## Profit
Flip, Hold or Wholetale: | hold |  |  | Buy | Your Home LLC
| 1426 Pleasant Garden Ln, Raleigh, NC 27604 | [5 empty] | Monthly Cash Flow |  | Hearing Date: |  | Use Template Estimate | no
Income |  |  | Immediate |  | Upon Sale
CMA: | 341700 | [7 empty] | Finalized: | yes
% Above/Below Market Sale: | -15% | 10% | [8 empty] | Zillow: | 2023-09-25 | 344600
Sale Price: | 375870 |  |  |  |  | 375870 |  |  | Anuual Growth: | 3% |  | 2023-10-18 | 342200
NonRefundable Deposit: |  |  | 0 |  | 0 | 41004 | <-- Apprication ----------- |  |  |  |  | 2024-03-12 | 336800
Rent: | 2225 | [6 empty] | 2225 | Sq Footage | 1898 |  | 2025-02-03 | 341700
|  | Net Income: | Net Income: | 0 | 416874 |  | 2225 |  |  |  |  | 2025-05-15 | 343400
Expenses
Reinstatment Cost 1st: | 15392.15 |  | -15392.15 |  |  |  | <-- Approx Pay-Down |  | If the Subject To Value is finalized, zero-out the Pay-Down savings
Subject To 1st:Truist | 3.375% | 131630 |  |  | -131630
Reinstatment Cost 2st: |  |  |  |  | 0 |  | 0 | [7 empty] | loan Balance | Rate | Annual Payment
Subject To 2st:Notes | 10% |  |  |  | 0 |  | 0 | [6 empty] | liens | 31154 | 0%
Liens - IRS & HOA |  | 31154 |  |  | -31154 | [8 empty] | Private money | 119000 | 10% | 11900
Partners Share % | 0% | [12 empty] | Wells Fargo | 131630 | 3.375% | 4442.5125
or Seller Payout: | 20000 |  | -20000 | [11 empty] | Total Debt | Effect Rate | Total Payments
HOA Fees(Catch Up) |  | 0 | 0 | [5 empty] | Yellow cells can be edited | [5 empty] | 281784 | 5.8% | 16342.5125
Months Carried | 33.2
Mortgage Payment: | 1081.8154 | [5 empty] | -1081.8154 |  | Do not edit Green cells. They are highlighted only to show profit
Private Money | 891.5663 | [5 empty] | -891.5663
Property Insurance | 0 | [5 empty] | 0
Property Tax: | 41.378 | [5 empty] | -41.378
HOA Fees (monthly) | 2.6422 | [5 empty] | -2.6422
Electric | 10.809 | [5 empty] | -10.809
Gas | 12.4726 | [5 empty] | -12.4726
water | 99.9295 | [5 empty] | -99.9295
Carrying Cost | 2140.613 |  | 0
Private Lender Rate: | 10% | yes
Duke Electric | 3.5911 |  |  | 111000 | -111000 |  |  |  | Carrying Cost | 64.4763 |  |  |  | 925
Mortgage Payment | 359.416 |  | -359.416
Private Money | 296.2088 |  | -296.2088
Casa Lending | 0 | 0 |  |  | 0 |  |  |  | Total Debt: | 273784
Insurance Payments | 33.2 | 2.6% |  |  | -359845.6368
Water | 4.1438 | 2.4% |  |  | -41458.8261
Natural Gas | 0.87782 | 48 | [6 empty] | Purchase Cost | 182784
HOA | 13.7472 |  |  |  | 0
Property Taxes | 23.3618 |  | -23.3618 | [5 empty] | Out of Pocket | 36071.1366
Excavator Rental | 0 |  |  |  | 0
Lawn | 0 | Net Expenses: |  | -36071.1366 | -675088.4629 |  | 84.387 |  | PL Balance +Interest
Carrying Cost | 73402.88 |  |  | 74928.8634 | -258214.4629
|  |  |  | Long Term Profit: |  | -183285.5995 |  |  | Partners Profit Share | Our Profit Share
|  |  |  | Cash Flow Profit for Months: |  |  | 33.2 | 2801.65
[5 empty] | Gross Profit: |  |  | -180483.9495 | 0 | -180483.9495
Capital Gains Tax | 15% | [5 empty] | Capital Gains |  | 0 | 27072.5924
Chartiable Contribution: | 10% | 15% | -15341.1357 |  |  |  | Gross Profit: |  | 0 | -153411.357
Rehab Cost Detail
Gnatt Chart | 47412.0563 |  | -47412.0563
Murphy %: | 10% |  |  |  |  | Murphy will be Zeroed-Out whe project is finalized
Murphy's Cut: | 0 |  | 0
Rehab Summary: |  |  | -47412.0563 |  |  | This value is carried up to cell C29, Labeled Rehab
Buying Closing Cost
Settlement Fee to Attorney: | 350
Probate Attorney | [5 empty] | Projected CashFlow Date |  |  | Months
Seller Doc Prep | 250 | [7 empty] | 33.2
Seller Doc Prep |  |  |  |  | Days Invested |  | Start Date |  | End Date
Wire Fee |  |  |  |  | 996 |  | 2023-10-04 |  | 2026-06-26 15:58
Wire Fee
Deed Package:
Indemnety:
Ttitle Search:
Cancelation Fee:
Overnight Express Fees:
Title Insurance: | 200
Affadavits:
Notice to Creditors Ad
Recording Fee Deed: | 90
Erecording Fee | 20
Excise Tax | 30
LLC Manager Fee
|  |  | 940 |  |  | This value is carried up to cell C36, Labeled Buying Closing Cost
Selling Closing Cost
Settlement Fee to Attorney:
Seller Doc Prep | 250
Seller concesson: | 0
Home Warrenty:
Recording Fee Deed:
Transfer Taxes - Wake County | 40
Revenue Stamps
LLC Manager Fee
|  |  | 290 |  |  | This value is carried up to cell C37, Labeled Selling Closing Cost
Formulas:
Your Home LLC = DAYS([Hearing Date:],[Monthly Cash Flow])

## MOG
|  | Multiple Offer Generator | [5 empty] | Hi Nikki, Thank you for the opportunity to make an offer on your property at 1426 Pleasant Garden Ln, Raleigh, NC 27604. I have several options I would like for you to consider. I also want to give you several very good reasons for you to work with us here at Buy Your Home LLC. 1. If you sell your home to us, you will incur no expense from the transaction. We will pay all: Closing Cost Attorney's Fees Realtor Commissions 2. We can close fast. It will be a matter of days, probably less than two weeks, when we can close at our attorney's office and get you your cash. 3. We cover the cost, time, and effort of paying any money due to any lender or HOA involved. | Buyers Copy | Hi Nikki, Thank you for the opportunity to make an offer on your property at 1426 Pleasant Garden Ln, Raleigh, NC 27604. I have several options I would like for you to consider. I also want to give you several very good reasons for you to work with us here at Buy Your Home LLC. 1. If you sell your home to us, you will incur no expense from the transaction. We will pay all: Closing Cost Attorney's Fees Realtor Commissions 2. We can close fast. It will be a matter of days, probably less than two weeks, when we can close at our attorney's office and get you your cash. 3. We cover the cost, time, and effort of paying any money due to any lender or HOA involved. Here are some purchase options for your consideration. They are presented in summary form and I am sure you will have some questions that I will be happy to take time needed to answer. Each option below will have more value than the one above it. Option 1: Cash plus Assumption of Mortgage This is a cash payment, at closing. We will take responsibility for the existing mortgage, HOA fees, and any liens that may be discovered until we are able to resell the property. This offer is: Cash: $20,000.00 Total Value: $20,000.00 Option 2: Cash plus Promissory Note The explanation for the cash component is the same as for option 1. However, 20.% of the value of the offer will be cash and 80.% will be in the form of a promissory note, complete with a Deed of Trust. The note will have a 24-month term that will pay simple interest at the rate of 4% per year. Cash: $4,000.00 12 Month Note: $36,000.00 Interest Earned: $2,880.00 $120.00 per month Total Value: $42,880.00 Option 3: Cash plus Beneficial Interest in Trust The explanation for the cash component is the same as for option 2. Instead of a note as in Option 2, you will share in the profit earned when the property is resold. The property will be placed into a trust that you will share a beneficial interest in. The advantage here is you will benefit from the appreciated value of the property, over time. You will receive quarterly reports on the financial status of the property. Cash: $10,000.00 Interest in Trust: 70.% Expected Sellers Profit: -$71,685.15 * Expected 3% appreciation per year Expected Value: -$61,685.15 ** After 24 months. Nikki, this offer is contingent upon a normal due diligence period. The values of each option are predicated on some assumptions that may need to be altered upon further discovery. The more we can learn from you, in advance, the more reliable these options may be considered. When you decide which offer you prefer, I will email you a contract along with an earnest money payment. We are ready to be of service in any way we can. This offer is based on Zillow's Zestimate of $341,700.00. We will clean and prepare the property for a quick resale. There is also an assumption that the property will need no rehab. If that turns out to not be true, an allowance will need to be made. In any case, that will be decided in the due diligence period of the contract. Sincerely, Wes Browning (919) 899-2104
Seller 1: | Nikki | Kulas | [6 empty] | no
Seller 2:
email:
Phone #:
Offer 1 | Traditional, All Cash
This is an all cash payment, at closing with no other allowances considered. Seller pays all Mortgages, liens, HOA expenses out of closings proceedings.
Seller's Equity
| Sales Price | ARV | Debt |  |  | BYH's Profit
| 180784 | 341700 | 162784 |  | 18000 | 144844.8634
|  |  | BYH Out of Pocket: | 36071.1366
|  |  | BYH Profit/Out of Pocket: | 401.6% | 10% |  | X | Here are some purchase options for your consideration. They are presented in summary form and I am sure you will have some questions that I will be happy to take time needed to answer. Each option below will have more value than the one above it.
|  |  | Buy Your Home's % of Profit: | 88.95% | less than Opt 2
Offer 2 | Cash plus Assumption of Mortgage |  | *This is the default values from the Profit Sheet. |  |  |  | 0
| Cash payment in conjunction with taking the existing mortgage subject to: | [6 empty] | Option 0: Traditional, All Cash This is a, traditional, all cash purchase, at closing with no other allowances considered. Seller pays all mortgages, liens, HOA expenses, etc., out of closings disbursements. This option has the smallest value for the seller. Our cash offer is: Cash: $180,784.00 Total Value: $18,000.00
After reinstating existing loans and HOA fees
Seller's Total Value
| Cash |  |  |  |  | BYH's Profit
| 20000 | <- The default value form profit sheet |  |  | 20000 | -153411.357
|  |  | BYH Out of Pocket: | 36071.1366 |  |  | 1
|  |  | BYH Profit/Out of Pocket: | -425.3% |  |  | x | Option 1: Cash plus Assumption of Mortgage This is a cash payment, at closing. We will take responsibility for the existing mortgage, HOA fees, and any liens that may be discovered until we are able to resell the property. This offer is: Cash: $20,000.00 Total Value: $20,000.00
|  |  | Buy Your Home's % of Profit: | 115%
Offer 3 | Cash plus Promissory Note |  | - this is the one to stear seller to:
| Cash payment in conjunction with taking the existing mortgage subject to: | [6 empty] | This is a cash payment, at closing, in conjunction with reinstating the existing mortgage taking responsibility for those payments, HOA fees and other liens that may be discovered. Our cash offer is:
| After reinstating existing loans and HOA fees | [5 empty] | 2
[7 empty] | x | Option 2: Cash plus Promissory Note The explanation for the cash component is the same as for option 1. However, 20.% of the value of the offer will be cash and 80.% will be in the form of a promissory note, complete with a Deed of Trust. The note will have a 24-month term that will pay simple interest at the rate of 4% per year. Cash: $4,000.00 12 Month Note: $36,000.00 Interest Earned: $2,880.00 $120.00 per month Total Value: $42,880.00
|  | Note is a simple interest note for: | Months |  | (Based on Current Valuation)
| Value added to Note: | 20000 | 24 |  | Seller's Total Value
| Cash | Note | Interest Earned | Interest Rate |  | BYH's Profit
| 4000 | 36000 | 2880 | 4% | 42880 | -176291.357
| 20% | 80%
|  |  | BYH Out of Pocket: | 20071.1366
|  |  | BYH Profit/Out of Pocket: | -878.3%
|  |  | Buy Your Home's % of Profit: | 132.1% |  |  | 3
Offer 4 | Cash plus Beneficial Interest in Trust | [5 empty] | x | Option 3: Cash plus Beneficial Interest in Trust The explanation for the cash component is the same as for option 2. Instead of a note as in Option 2, you will share in the profit earned when the property is resold. The property will be placed into a trust that you will share a beneficial interest in. The advantage here is you will benefit from the appreciated value of the property, over time. You will receive quarterly reports on the financial status of the property. Cash: $10,000.00 Interest in Trust: 70.% Expected Sellers Profit: -$71,685.15 * Expected 3% appreciation per year Expected Value: -$61,685.15 ** After 24 months.
Cash payment in conjunction with taking the existing mortgage subject to:
After reinstating existing loans and HOA fees
Profit split is a split of the profits upon the eventual sale of the pproperty.
Profits will be calculated after deducting all expenses incurred from the sales price
(Based on Future Valuation)
|  | Trust Future Profit | Seller's Profit Sharing Percent | Seller's Profit Share | Seller's Total Value
| Cash | Trust Future Profit | Seller's Profit Sharing Percent | Sellers Share Profit |  | BYH's Profit
| 10000 | -102407.357 | 70% | -71685.1499 | -61685.1499 | -30722.2071
*This precentage is not set in Profit sheet. It is for proposal only.
|  |  | BYH Out of Pocket: | 26071.1366 |  |  | X | Nikki, this offer is contingent upon a normal due diligence period. The values of each option are predicated on some assumptions that may need to be altered upon further discovery. The more we can learn from you, in advance, the more reliable these options may be considered. When you decide which offer you prefer, I will email you a contract along with an earnest money payment. We are ready to be of service in any way we can.
|  |  | BYH Profit/Out of Pocket: | -117.8%
|  |  | Buy Your Home's % of Profit: | 33.25%
| Personalize Note |  | {alt}{enter] = carrage return
This offer is based on Zillow's Zestimate of $341,700.00. We will clean and prepare the property for a quick resale. There is also an assumption that the property will need no rehab. If that turns out to not be true, an allowance will need to be made. In any case, that will be decided in the due diligence period of the contract.
[7 empty] | X | This offer is based on Zillow's Zestimate of $341,700.00. We will clean and prepare the property for a quick resale. There is also an assumption that the property will need no rehab. If that turns out to not be true, an allowance will need to be made. In any case, that will be decided in the due diligence period of the contract.
[7 empty] | X | Sincerely, Wes Browning
[6 empty] | Foreclosure Leads |  | (919) 899-4954
[6 empty] | Liberty Leads | X | (919) 899-2104

## Contact
Vendor | Phone Number | Contact | Acct/Policy | Email | Purpose
Sellers
Estate of Sharrice Y Stagg |  |  | SS#: 231 04 1014 | birthday: 11/12/1971
Paticai Baker - Adminstrator |  |  | 936 52 3090
Mortgage | 800 274 7025 |  |  | Wiring Instructions Acct#: 3000500412, Routing#: 121000248, Wells Fargo Bank NA, 420 Montgomery St, Sanfransico, CA 94104
Wells Fargo Home Mortgage | Fax: 866 278 1179 |  | 0211198205 |  | sent on 09/27/2023
Brock & Scott | 919 872 5466 x1147
| HOA |  | User Name:WesBrowning PW:w3638B0@ | https://www.homewisedocs.com/login
Reosourch Property Management | ‪(919) 240-4045‬ | Meshann Chalmers | www.rpmpropertypros.com | User:BuyYourHome PW:w3638B0@
HOA Acct #:108902341
NREIG | 770 734 1523 |  |  | 952.79 | 2024-02-01
Plumber GWE Plumbing | 2340 Sapphire Valley Dr Ral 27604 | gweplbg@gmail.com |  | 1905.58 |  | To | Subject | Sent | Size | Categories
[6 empty] | DefaultCFC@Truist.com | 5008 Larchmont Dr - Loan 9015 2144 11-5998 | 10:42 | 478 KB
Insurance National Real Estate Insurance Group LLC |  |  |  | 1905.58
Rani Walker | 678 329 0123 | RWalker@insurancehub.com
Customer Care Specialist
InsuranceHub Leavitt Agency
Phone/SMS/Fax: 678.329.0123 ¦ insurancehub.com
Becki Miron | 678.685.3277 | BMiron@insurancehub.com
Account Manager
InsuranceHub Leavitt Agency
Phone/SMS/Fax: 678.685.3277 ¦ insurancehub.com

## Carrying
Duke Electric |  | Mortgage Payment paid after Reinstatement |  | Private Money |  | Casa Lending |  | Insurance Payments |  | Water |  | Natural Gas |  | HOA |  | Property Taxes |  |  | Excavator Rental |  | Lawn
Date | payment | Date | payment | Date | payment | Date | payment | Date | payment | Date | payment | Date | payment | Date | payment | Date | payment | Paid in Escrow | Date | payment | Date | payment | Include | Category | Date | Vendor | Description | Amount | Source | Invoice # | Source File | Status | Notes
2023-11-06 | 50.55 | 2024-01-04 | 2858.37 | 2023-11-01 | 925 |  |  | 2023-12-03 | 199.39 | 2023-10-02 | 53.96 | 2023-10-10 | 30.7 | 2024-06-03 | 346.23 | 2023-11-13 | 2334.53 | [5 empty] | Yes | Duke Electric | 2023-11-06 |  |  | 50.55 | Migrated Carrying Grid |  | 19_Project Management - 1426 Pleasant Garden Ln orignianl .xlsx | Migrated | Source Carrying!A4:B4
2023-12-05 | 24.66 | 2024-03-12 | 1905.58 | 2023-12-01 | 925 |  |  | 2024-01-03 | 199.39 | 2023-11-01 | 66.12 | 2023-11-07 | 10.7 | 2024-07-09 | 241.57 | 2024-09-11 | 3101.83 | [5 empty] | Yes | Duke Electric | 2023-12-05 |  |  | 24.66 | Migrated Carrying Grid |  | 19_Project Management - 1426 Pleasant Garden Ln orignianl .xlsx | Migrated | Source Carrying!A5:B5
2024-01-10 | 30.01 | 2024-04-01 | 952.79 | 2023-12-31 | 925 |  |  | 2024-02-03 | 134.34 | 2023-12-01 | 50.62 | 2023-12-08 | 10.7 | 2025-01-13 | 253.65 | 2025-09-11 |  | -3101.83 |  |  |  |  | Yes | Duke Electric | 2024-01-10 |  |  | 30.01 | Migrated Carrying Grid |  | 19_Project Management - 1426 Pleasant Garden Ln orignianl .xlsx | Migrated | Source Carrying!A6:B6
2024-02-06 | 29.48 | 2024-05-01 | 1081.21 | 2024-01-04 | 925 |  |  | 2024-03-03 | 134.34 | 2024-01-02 | 50.62 | 2024-01-09 | 10.7 | 2025-05-15 | 25 | [7 empty] | Yes | Duke Electric | 2024-02-06 |  |  | 29.48 | Migrated Carrying Grid |  | 19_Project Management - 1426 Pleasant Garden Ln orignianl .xlsx | Migrated | Source Carrying!A7:B7
2024-03-06 | 29.48 | 2024-05-31 | 1081.21 | 2024-03-12 | 925 |  |  | 2024-04-01 | 94.65 | 2024-01-31 | 50.62 | 2024-02-09 | 11.99 | 2025-06-30 | 0 | [7 empty] | Yes | Duke Electric | 2024-03-06 |  |  | 29.48 | Migrated Carrying Grid |  | 19_Project Management - 1426 Pleasant Garden Ln orignianl .xlsx | Migrated | Source Carrying!A8:B8
2024-04-04 | 28.38 | 2024-06-01 | 1081.21 | 2024-04-01 | 925 |  |  | 2024-05-01 | 94.65 | 2024-03-01 | 50.62 | 2024-03-08 | 11.94 | 2025-07-16 | 253.65 | [7 empty] | Yes | Duke Electric | 2024-04-04 |  |  | 28.38 | Migrated Carrying Grid |  | 19_Project Management - 1426 Pleasant Garden Ln orignianl .xlsx | Migrated | Source Carrying!A9:B9
2024-05-06 | 64.41 | 2024-07-01 | 1081.21 | 2024-05-01 | 925 |  |  | 2024-05-31 | 94.65 | 2024-04-02 | 50.62 | 2024-04-09 | 10.7 | 2025-12-27 | 0 | [7 empty] | Yes | Duke Electric | 2024-05-06 |  |  | 64.41 | Migrated Carrying Grid |  | 19_Project Management - 1426 Pleasant Garden Ln orignianl .xlsx | Migrated | Source Carrying!A10:B10
2024-10-11 | 101.89 | 2024-07-31 | 1081.21 | 2024-05-31 | 925 |  |  | 2024-06-30 | 94.65 | 2024-05-02 | 50.62 | 2024-05-06 | -9.71 | 2026-01-15 | 253.65 | [7 empty] | Yes | Duke Electric | 2024-10-11 |  |  | 101.89 | Migrated Carrying Grid |  | 19_Project Management - 1426 Pleasant Garden Ln orignianl .xlsx | Migrated | Source Carrying!A11:B11
|  | 2024-07-31 | 1081.21 | 2024-06-28 | 925 |  |  | 2024-07-30 | 94.65 | 2024-05-06 | -9.71 |  |  | 2026-07-01 | 253.65 | [7 empty] | Yes | Mortgage Payment | 2024-01-04 |  |  | 2858.37 | Migrated Carrying Grid |  | 19_Project Management - 1426 Pleasant Garden Ln orignianl .xlsx | Migrated | Source Carrying!D6:E6
|  | 2024-08-30 | 1081.21 | 2024-07-28 | 925 |  |  | 2024-08-29 | 94.65 | [13 empty] | Yes | Mortgage Payment | 2024-03-12 |  |  | 1905.58 | Migrated Carrying Grid |  | 19_Project Management - 1426 Pleasant Garden Ln orignianl .xlsx | Migrated | Source Carrying!D7:E7
|  | 2024-09-29 | 1081.21 | 2024-08-27 | 925 |  |  | 2024-09-28 | 94.65 | [13 empty] | Yes | Mortgage Payment | 2024-04-01 |  |  | 952.79 | Migrated Carrying Grid |  | 19_Project Management - 1426 Pleasant Garden Ln orignianl .xlsx | Migrated | Source Carrying!D8:E8
|  | 2024-10-29 | 1081.21 | 2024-09-26 | 925 |  |  | 2024-10-28 | 94.65 | [13 empty] | Yes | Mortgage Payment | 2024-05-01 |  |  | 1081.21 | Migrated Carrying Grid |  | 19_Project Management - 1426 Pleasant Garden Ln orignianl .xlsx | Migrated | Source Carrying!D9:E9
|  | 2024-11-28 | 1081.21 | 2024-10-26 | 925 |  |  | 2024-11-27 | 94.65 | [13 empty] | Yes | Mortgage Payment | 2024-05-31 |  |  | 1081.21 | Migrated Carrying Grid |  | 19_Project Management - 1426 Pleasant Garden Ln orignianl .xlsx | Migrated | Source Carrying!D10:E10
|  | 2024-12-28 | 1081.21 | 2024-11-25 | 925 |  |  | 2024-12-27 | 94.65 | [13 empty] | Yes | Mortgage Payment | 2024-06-01 |  |  | 1081.21 | Migrated Carrying Grid |  | 19_Project Management - 1426 Pleasant Garden Ln orignianl .xlsx | Migrated | Source Carrying!D11:E11
|  | 2025-01-27 | 1081.21 | 2024-12-25 | 925 |  |  | 2025-01-03 | 94.65 | [13 empty] | Yes | Mortgage Payment | 2024-07-01 |  |  | 1081.21 | Migrated Carrying Grid |  | 19_Project Management - 1426 Pleasant Garden Ln orignianl .xlsx | Migrated | Source Carrying!D12:E12
|  | 2025-02-26 | 1209.23 | 2025-01-28 | 925 |  |  | 2025-02-02 | 94.65 | [13 empty] | Yes | Mortgage Payment | 2024-07-31 |  |  | 1081.21 | Migrated Carrying Grid |  | 19_Project Management - 1426 Pleasant Garden Ln orignianl .xlsx | Migrated | Source Carrying!D13:E13
|  | 2025-03-28 | 1209.23 | 2025-02-27 | 925 |  |  | 2025-03-04 | 94.65 | [13 empty] | Yes | Mortgage Payment | 2024-07-31 |  |  | 1081.21 | Migrated Carrying Grid |  | 19_Project Management - 1426 Pleasant Garden Ln orignianl .xlsx | Migrated | Source Carrying!D14:E14
|  | 2025-04-27 | 1209.23 | 2025-03-29 | 925 |  |  | 2025-04-03 | 94.65 | [13 empty] | Yes | Mortgage Payment | 2024-08-30 |  |  | 1081.21 | Migrated Carrying Grid |  | 19_Project Management - 1426 Pleasant Garden Ln orignianl .xlsx | Migrated | Source Carrying!D15:E15
|  | 2025-05-27 | 1209.23 | 2025-04-28 | 925 |  |  | 2025-05-03 | 94.65 | [13 empty] | Yes | Mortgage Payment | 2024-09-29 |  |  | 1081.21 | Migrated Carrying Grid |  | 19_Project Management - 1426 Pleasant Garden Ln orignianl .xlsx | Migrated | Source Carrying!D16:E16
|  | 2025-06-26 | 1209.23 | 2025-05-28 | 925 |  |  | 2025-06-02 | 94.65 | [13 empty] | Yes | Mortgage Payment | 2024-10-29 |  |  | 1081.21 | Migrated Carrying Grid |  | 19_Project Management - 1426 Pleasant Garden Ln orignianl .xlsx | Migrated | Source Carrying!D17:E17
|  | 2025-07-26 | 1209.23 | 2025-06-27 | 925 |  |  | 2025-07-02 | 94.65 | [13 empty] | Yes | Mortgage Payment | 2024-11-28 |  |  | 1081.21 | Migrated Carrying Grid |  | 19_Project Management - 1426 Pleasant Garden Ln orignianl .xlsx | Migrated | Source Carrying!D18:E18
|  | 2025-08-25 | 1209.23 | 2025-07-27 | 925 |  |  | 2025-08-01 | 94.65 | [13 empty] | Yes | Mortgage Payment | 2024-12-28 |  |  | 1081.21 | Migrated Carrying Grid |  | 19_Project Management - 1426 Pleasant Garden Ln orignianl .xlsx | Migrated | Source Carrying!D19:E19
|  | 2025-09-24 | 1209.23 | 2025-08-26 | 925 |  |  | 2025-08-31 | 94.65 | [13 empty] | Yes | Mortgage Payment | 2025-01-27 |  |  | 1081.21 | Migrated Carrying Grid |  | 19_Project Management - 1426 Pleasant Garden Ln orignianl .xlsx | Migrated | Source Carrying!D20:E20
|  | 2025-10-24 | 1209.23 | 2025-09-25 | 925 |  |  | 2025-09-30 | 94.65 | [13 empty] | Yes | Mortgage Payment | 2025-02-26 |  |  | 1209.23 | Migrated Carrying Grid |  | 19_Project Management - 1426 Pleasant Garden Ln orignianl .xlsx | Migrated | Source Carrying!D21:E21
|  | 2025-11-23 | 1209.23 | 2025-10-25 | 925 |  |  | 2025-10-30 | 94.65 | [13 empty] | Yes | Mortgage Payment | 2025-03-28 |  |  | 1209.23 | Migrated Carrying Grid |  | 19_Project Management - 1426 Pleasant Garden Ln orignianl .xlsx | Migrated | Source Carrying!D22:E22
|  | 2026-01-01 | 1209.23 | 2025-11-24 | 925 |  |  | 2025-11-29 | 94.65 | [13 empty] | Yes | Mortgage Payment | 2025-04-27 |  |  | 1209.23 | Migrated Carrying Grid |  | 19_Project Management - 1426 Pleasant Garden Ln orignianl .xlsx | Migrated | Source Carrying!D23:E23
|  | 2026-01-31 | 980.87 | 2025-12-24 | 925 |  |  | 2025-12-29 | 94.65 | [13 empty] | Yes | Mortgage Payment | 2025-05-27 |  |  | 1209.23 | Migrated Carrying Grid |  | 19_Project Management - 1426 Pleasant Garden Ln orignianl .xlsx | Migrated | Source Carrying!D24:E24
|  | 2026-03-02 | 980.87 | 2026-01-23 | 925 |  |  | 2026-01-28 | 94.65 | [13 empty] | Yes | Mortgage Payment | 2025-06-26 |  |  | 1209.23 | Migrated Carrying Grid |  | 19_Project Management - 1426 Pleasant Garden Ln orignianl .xlsx | Migrated | Source Carrying!D25:E25
|  | 2026-04-01 | 980.87 | 2026-02-22 | 925 |  |  | 2026-02-27 | 94.65 | [13 empty] | Yes | Mortgage Payment | 2025-07-26 |  |  | 1209.23 | Migrated Carrying Grid |  | 19_Project Management - 1426 Pleasant Garden Ln orignianl .xlsx | Migrated | Source Carrying!D26:E26
|  | 2026-05-01 | 980.87 | 2026-03-24 | 925 |  |  | 2026-03-29 | 94.65 | [13 empty] | Yes | Mortgage Payment | 2025-08-25 |  |  | 1209.23 | Migrated Carrying Grid |  | 19_Project Management - 1426 Pleasant Garden Ln orignianl .xlsx | Migrated | Source Carrying!D27:E27
|  |  |  | 2026-04-23 | 925 |  |  | 2026-04-28 | 94.65 | [13 empty] | Yes | Mortgage Payment | 2025-09-24 |  |  | 1209.23 | Migrated Carrying Grid |  | 19_Project Management - 1426 Pleasant Garden Ln orignianl .xlsx | Migrated | Source Carrying!D28:E28
|  |  |  | 2026-05-23 | 925 |  |  | 2026-05-28 | 94.65 | [13 empty] | Yes | Mortgage Payment | 2025-10-24 |  |  | 1209.23 | Migrated Carrying Grid |  | 19_Project Management - 1426 Pleasant Garden Ln orignianl .xlsx | Migrated | Source Carrying!D29:E29
[23 empty] | Yes | Mortgage Payment | 2025-11-23 |  |  | 1209.23 | Migrated Carrying Grid |  | 19_Project Management - 1426 Pleasant Garden Ln orignianl .xlsx | Migrated | Source Carrying!D30:E30
[23 empty] | Yes | Mortgage Payment | 2026-01-01 |  |  | 1209.23 | Migrated Carrying Grid |  | 19_Project Management - 1426 Pleasant Garden Ln orignianl .xlsx | Migrated | Source Carrying!D31:E31
[23 empty] | Yes | Mortgage Payment | 2026-01-31 |  |  | 980.87 | Migrated Carrying Grid |  | 19_Project Management - 1426 Pleasant Garden Ln orignianl .xlsx | Migrated | Source Carrying!D32:E32
[23 empty] | Yes | Mortgage Payment | 2026-03-02 |  |  | 980.87 | Migrated Carrying Grid |  | 19_Project Management - 1426 Pleasant Garden Ln orignianl .xlsx | Migrated | Source Carrying!D33:E33
[23 empty] | Yes | Mortgage Payment | 2026-04-01 |  |  | 980.87 | Migrated Carrying Grid |  | 19_Project Management - 1426 Pleasant Garden Ln orignianl .xlsx | Migrated | Source Carrying!D34:E34
[23 empty] | Yes | Mortgage Payment | 2026-05-01 |  |  | 980.87 | Migrated Carrying Grid |  | 19_Project Management - 1426 Pleasant Garden Ln orignianl .xlsx | Migrated | Source Carrying!D35:E35
[23 empty] | Yes | Private Money | 2023-11-01 |  |  | 925 | Migrated Carrying Grid |  | 19_Project Management - 1426 Pleasant Garden Ln orignianl .xlsx | Migrated | Source Carrying!G4:H4
[23 empty] | Yes | Private Money | 2023-12-01 |  |  | 925 | Migrated Carrying Grid |  | 19_Project Management - 1426 Pleasant Garden Ln orignianl .xlsx | Migrated | Source Carrying!G5:H5
[23 empty] | Yes | Private Money | 2023-12-31 |  |  | 925 | Migrated Carrying Grid |  | 19_Project Management - 1426 Pleasant Garden Ln orignianl .xlsx | Migrated | Source Carrying!G6:H6
[23 empty] | Yes | Private Money | 2024-01-04 |  |  | 925 | Migrated Carrying Grid |  | 19_Project Management - 1426 Pleasant Garden Ln orignianl .xlsx | Migrated | Source Carrying!G7:H7
[23 empty] | Yes | Private Money | 2024-03-12 |  |  | 925 | Migrated Carrying Grid |  | 19_Project Management - 1426 Pleasant Garden Ln orignianl .xlsx | Migrated | Source Carrying!G8:H8
[23 empty] | Yes | Private Money | 2024-04-01 |  |  | 925 | Migrated Carrying Grid |  | 19_Project Management - 1426 Pleasant Garden Ln orignianl .xlsx | Migrated | Source Carrying!G9:H9
| 358.86 |  | 35916.27 |  | 29600 |  | 0 |  | 3317.66 |  | 414.09 |  | 87.72 |  | 1373.75 |  | 2334.53 |  |  | 0 |  | 0 | Yes | Private Money | 2024-05-01 |  |  | 925 | Migrated Carrying Grid |  | 19_Project Management - 1426 Pleasant Garden Ln orignianl .xlsx | Migrated | Source Carrying!G10:H10
[23 empty] | Yes | Private Money | 2024-05-31 |  |  | 925 | Migrated Carrying Grid |  | 19_Project Management - 1426 Pleasant Garden Ln orignianl .xlsx | Migrated | Source Carrying!G11:H11
[23 empty] | Yes | Private Money | 2024-06-28 |  |  | 925 | Migrated Carrying Grid |  | 19_Project Management - 1426 Pleasant Garden Ln orignianl .xlsx | Migrated | Source Carrying!G12:H12
[23 empty] | Yes | Private Money | 2024-07-28 |  |  | 925 | Migrated Carrying Grid |  | 19_Project Management - 1426 Pleasant Garden Ln orignianl .xlsx | Migrated | Source Carrying!G13:H13
[23 empty] | Yes | Private Money | 2024-08-27 |  |  | 925 | Migrated Carrying Grid |  | 19_Project Management - 1426 Pleasant Garden Ln orignianl .xlsx | Migrated | Source Carrying!G14:H14
[23 empty] | Yes | Private Money | 2024-09-26 |  |  | 925 | Migrated Carrying Grid |  | 19_Project Management - 1426 Pleasant Garden Ln orignianl .xlsx | Migrated | Source Carrying!G15:H15
[23 empty] | Yes | Private Money | 2024-10-26 |  |  | 925 | Migrated Carrying Grid |  | 19_Project Management - 1426 Pleasant Garden Ln orignianl .xlsx | Migrated | Source Carrying!G16:H16
[23 empty] | Yes | Private Money | 2024-11-25 |  |  | 925 | Migrated Carrying Grid |  | 19_Project Management - 1426 Pleasant Garden Ln orignianl .xlsx | Migrated | Source Carrying!G17:H17
[23 empty] | Yes | Private Money | 2024-12-25 |  |  | 925 | Migrated Carrying Grid |  | 19_Project Management - 1426 Pleasant Garden Ln orignianl .xlsx | Migrated | Source Carrying!G18:H18
[23 empty] | Yes | Private Money | 2025-01-28 |  |  | 925 | Migrated Carrying Grid |  | 19_Project Management - 1426 Pleasant Garden Ln orignianl .xlsx | Migrated | Source Carrying!G19:H19
[23 empty] | Yes | Private Money | 2025-02-27 |  |  | 925 | Migrated Carrying Grid |  | 19_Project Management - 1426 Pleasant Garden Ln orignianl .xlsx | Migrated | Source Carrying!G20:H20
[23 empty] | Yes | Private Money | 2025-03-29 |  |  | 925 | Migrated Carrying Grid |  | 19_Project Management - 1426 Pleasant Garden Ln orignianl .xlsx | Migrated | Source Carrying!G21:H21
[23 empty] | Yes | Private Money | 2025-04-28 |  |  | 925 | Migrated Carrying Grid |  | 19_Project Management - 1426 Pleasant Garden Ln orignianl .xlsx | Migrated | Source Carrying!G22:H22
[23 empty] | Yes | Private Money | 2025-05-28 |  |  | 925 | Migrated Carrying Grid |  | 19_Project Management - 1426 Pleasant Garden Ln orignianl .xlsx | Migrated | Source Carrying!G23:H23
[23 empty] | Yes | Private Money | 2025-06-27 |  |  | 925 | Migrated Carrying Grid |  | 19_Project Management - 1426 Pleasant Garden Ln orignianl .xlsx | Migrated | Source Carrying!G24:H24
[23 empty] | Yes | Private Money | 2025-07-27 |  |  | 925 | Migrated Carrying Grid |  | 19_Project Management - 1426 Pleasant Garden Ln orignianl .xlsx | Migrated | Source Carrying!G25:H25
[23 empty] | Yes | Private Money | 2025-08-26 |  |  | 925 | Migrated Carrying Grid |  | 19_Project Management - 1426 Pleasant Garden Ln orignianl .xlsx | Migrated | Source Carrying!G26:H26
[23 empty] | Yes | Private Money | 2025-09-25 |  |  | 925 | Migrated Carrying Grid |  | 19_Project Management - 1426 Pleasant Garden Ln orignianl .xlsx | Migrated | Source Carrying!G27:H27
[23 empty] | Yes | Private Money | 2025-10-25 |  |  | 925 | Migrated Carrying Grid |  | 19_Project Management - 1426 Pleasant Garden Ln orignianl .xlsx | Migrated | Source Carrying!G28:H28
[23 empty] | Yes | Private Money | 2025-11-24 |  |  | 925 | Migrated Carrying Grid |  | 19_Project Management - 1426 Pleasant Garden Ln orignianl .xlsx | Migrated | Source Carrying!G29:H29
[23 empty] | Yes | Private Money | 2025-12-24 |  |  | 925 | Migrated Carrying Grid |  | 19_Project Management - 1426 Pleasant Garden Ln orignianl .xlsx | Migrated | Source Carrying!G30:H30
[23 empty] | Yes | Private Money | 2026-01-23 |  |  | 925 | Migrated Carrying Grid |  | 19_Project Management - 1426 Pleasant Garden Ln orignianl .xlsx | Migrated | Source Carrying!G31:H31
[23 empty] | Yes | Private Money | 2026-02-22 |  |  | 925 | Migrated Carrying Grid |  | 19_Project Management - 1426 Pleasant Garden Ln orignianl .xlsx | Migrated | Source Carrying!G32:H32
[23 empty] | Yes | Private Money | 2026-03-24 |  |  | 925 | Migrated Carrying Grid |  | 19_Project Management - 1426 Pleasant Garden Ln orignianl .xlsx | Migrated | Source Carrying!G33:H33
[23 empty] | Yes | Private Money | 2026-04-23 |  |  | 925 | Migrated Carrying Grid |  | 19_Project Management - 1426 Pleasant Garden Ln orignianl .xlsx | Migrated | Source Carrying!G34:H34
[23 empty] | Yes | Private Money | 2026-05-23 |  |  | 925 | Migrated Carrying Grid |  | 19_Project Management - 1426 Pleasant Garden Ln orignianl .xlsx | Migrated | Source Carrying!G35:H35
[23 empty] | Yes | Insurance Payments | 2023-12-03 |  |  | 199.39 | Migrated Carrying Grid |  | 19_Project Management - 1426 Pleasant Garden Ln orignianl .xlsx | Migrated | Source Carrying!J5:K5
[23 empty] | Yes | Insurance Payments | 2024-01-03 |  |  | 199.39 | Migrated Carrying Grid |  | 19_Project Management - 1426 Pleasant Garden Ln orignianl .xlsx | Migrated | Source Carrying!J6:K6
[23 empty] | Yes | Insurance Payments | 2024-02-03 |  |  | 134.34 | Migrated Carrying Grid |  | 19_Project Management - 1426 Pleasant Garden Ln orignianl .xlsx | Migrated | Source Carrying!J7:K7
[23 empty] | Yes | Insurance Payments | 2024-03-03 |  |  | 134.34 | Migrated Carrying Grid |  | 19_Project Management - 1426 Pleasant Garden Ln orignianl .xlsx | Migrated | Source Carrying!J8:K8
[23 empty] | Yes | Insurance Payments | 2024-04-01 |  |  | 94.65 | Migrated Carrying Grid |  | 19_Project Management - 1426 Pleasant Garden Ln orignianl .xlsx | Migrated | Source Carrying!J9:K9
[23 empty] | Yes | Insurance Payments | 2024-05-01 |  |  | 94.65 | Migrated Carrying Grid |  | 19_Project Management - 1426 Pleasant Garden Ln orignianl .xlsx | Migrated | Source Carrying!J10:K10
[23 empty] | Yes | Insurance Payments | 2024-05-31 |  |  | 94.65 | Migrated Carrying Grid |  | 19_Project Management - 1426 Pleasant Garden Ln orignianl .xlsx | Migrated | Source Carrying!J11:K11
[23 empty] | Yes | Insurance Payments | 2024-06-30 |  |  | 94.65 | Migrated Carrying Grid |  | 19_Project Management - 1426 Pleasant Garden Ln orignianl .xlsx | Migrated | Source Carrying!J12:K12
[23 empty] | Yes | Insurance Payments | 2024-07-30 |  |  | 94.65 | Migrated Carrying Grid |  | 19_Project Management - 1426 Pleasant Garden Ln orignianl .xlsx | Migrated | Source Carrying!J13:K13
[23 empty] | Yes | Insurance Payments | 2024-08-29 |  |  | 94.65 | Migrated Carrying Grid |  | 19_Project Management - 1426 Pleasant Garden Ln orignianl .xlsx | Migrated | Source Carrying!J14:K14
[23 empty] | Yes | Insurance Payments | 2024-09-28 |  |  | 94.65 | Migrated Carrying Grid |  | 19_Project Management - 1426 Pleasant Garden Ln orignianl .xlsx | Migrated | Source Carrying!J15:K15
[23 empty] | Yes | Insurance Payments | 2024-10-28 |  |  | 94.65 | Migrated Carrying Grid |  | 19_Project Management - 1426 Pleasant Garden Ln orignianl .xlsx | Migrated | Source Carrying!J16:K16
[23 empty] | Yes | Insurance Payments | 2024-11-27 |  |  | 94.65 | Migrated Carrying Grid |  | 19_Project Management - 1426 Pleasant Garden Ln orignianl .xlsx | Migrated | Source Carrying!J17:K17
[23 empty] | Yes | Insurance Payments | 2024-12-27 |  |  | 94.65 | Migrated Carrying Grid |  | 19_Project Management - 1426 Pleasant Garden Ln orignianl .xlsx | Migrated | Source Carrying!J18:K18
[23 empty] | Yes | Insurance Payments | 2025-01-03 |  |  | 94.65 | Migrated Carrying Grid |  | 19_Project Management - 1426 Pleasant Garden Ln orignianl .xlsx | Migrated | Source Carrying!J19:K19
[23 empty] | Yes | Insurance Payments | 2025-02-02 |  |  | 94.65 | Migrated Carrying Grid |  | 19_Project Management - 1426 Pleasant Garden Ln orignianl .xlsx | Migrated | Source Carrying!J20:K20
[23 empty] | Yes | Insurance Payments | 2025-03-04 |  |  | 94.65 | Migrated Carrying Grid |  | 19_Project Management - 1426 Pleasant Garden Ln orignianl .xlsx | Migrated | Source Carrying!J21:K21
[23 empty] | Yes | Insurance Payments | 2025-04-03 |  |  | 94.65 | Migrated Carrying Grid |  | 19_Project Management - 1426 Pleasant Garden Ln orignianl .xlsx | Migrated | Source Carrying!J22:K22
[23 empty] | Yes | Insurance Payments | 2025-05-03 |  |  | 94.65 | Migrated Carrying Grid |  | 19_Project Management - 1426 Pleasant Garden Ln orignianl .xlsx | Migrated | Source Carrying!J23:K23
[23 empty] | Yes | Insurance Payments | 2025-06-02 |  |  | 94.65 | Migrated Carrying Grid |  | 19_Project Management - 1426 Pleasant Garden Ln orignianl .xlsx | Migrated | Source Carrying!J24:K24
[23 empty] | Yes | Insurance Payments | 2025-07-02 |  |  | 94.65 | Migrated Carrying Grid |  | 19_Project Management - 1426 Pleasant Garden Ln orignianl .xlsx | Migrated | Source Carrying!J25:K25
[23 empty] | Yes | Insurance Payments | 2025-08-01 |  |  | 94.65 | Migrated Carrying Grid |  | 19_Project Management - 1426 Pleasant Garden Ln orignianl .xlsx | Migrated | Source Carrying!J26:K26
[23 empty] | Yes | Insurance Payments | 2025-08-31 |  |  | 94.65 | Migrated Carrying Grid |  | 19_Project Management - 1426 Pleasant Garden Ln orignianl .xlsx | Migrated | Source Carrying!J27:K27
[23 empty] | Yes | Insurance Payments | 2025-09-30 |  |  | 94.65 | Migrated Carrying Grid |  | 19_Project Management - 1426 Pleasant Garden Ln orignianl .xlsx | Migrated | Source Carrying!J28:K28
[23 empty] | Yes | Insurance Payments | 2025-10-30 |  |  | 94.65 | Migrated Carrying Grid |  | 19_Project Management - 1426 Pleasant Garden Ln orignianl .xlsx | Migrated | Source Carrying!J29:K29
[23 empty] | Yes | Insurance Payments | 2025-11-29 |  |  | 94.65 | Migrated Carrying Grid |  | 19_Project Management - 1426 Pleasant Garden Ln orignianl .xlsx | Migrated | Source Carrying!J30:K30
[23 empty] | Yes | Insurance Payments | 2025-12-29 |  |  | 94.65 | Migrated Carrying Grid |  | 19_Project Management - 1426 Pleasant Garden Ln orignianl .xlsx | Migrated | Source Carrying!J31:K31
[23 empty] | Yes | Insurance Payments | 2026-01-28 |  |  | 94.65 | Migrated Carrying Grid |  | 19_Project Management - 1426 Pleasant Garden Ln orignianl .xlsx | Migrated | Source Carrying!J32:K32
[23 empty] | Yes | Insurance Payments | 2026-02-27 |  |  | 94.65 | Migrated Carrying Grid |  | 19_Project Management - 1426 Pleasant Garden Ln orignianl .xlsx | Migrated | Source Carrying!J33:K33
[23 empty] | Yes | Insurance Payments | 2026-03-29 |  |  | 94.65 | Migrated Carrying Grid |  | 19_Project Management - 1426 Pleasant Garden Ln orignianl .xlsx | Migrated | Source Carrying!J34:K34
[23 empty] | Yes | Insurance Payments | 2026-04-28 |  |  | 94.65 | Migrated Carrying Grid |  | 19_Project Management - 1426 Pleasant Garden Ln orignianl .xlsx | Migrated | Source Carrying!J35:K35
[23 empty] | Yes | Insurance Payments | 2026-05-28 |  |  | 94.65 | Migrated Carrying Grid |  | 19_Project Management - 1426 Pleasant Garden Ln orignianl .xlsx | Migrated | Source Carrying!J36:K36
[23 empty] | Yes | Water | 2023-10-02 |  |  | 53.96 | Migrated Carrying Grid |  | 19_Project Management - 1426 Pleasant Garden Ln orignianl .xlsx | Migrated | Source Carrying!M3:N3
[23 empty] | Yes | Water | 2023-11-01 |  |  | 66.12 | Migrated Carrying Grid |  | 19_Project Management - 1426 Pleasant Garden Ln orignianl .xlsx | Migrated | Source Carrying!M4:N4
[23 empty] | Yes | Water | 2023-12-01 |  |  | 50.62 | Migrated Carrying Grid |  | 19_Project Management - 1426 Pleasant Garden Ln orignianl .xlsx | Migrated | Source Carrying!M5:N5
[23 empty] | Yes | Water | 2024-01-02 |  |  | 50.62 | Migrated Carrying Grid |  | 19_Project Management - 1426 Pleasant Garden Ln orignianl .xlsx | Migrated | Source Carrying!M6:N6
[23 empty] | Yes | Water | 2024-01-31 |  |  | 50.62 | Migrated Carrying Grid |  | 19_Project Management - 1426 Pleasant Garden Ln orignianl .xlsx | Migrated | Source Carrying!M7:N7
[23 empty] | Yes | Water | 2024-03-01 |  |  | 50.62 | Migrated Carrying Grid |  | 19_Project Management - 1426 Pleasant Garden Ln orignianl .xlsx | Migrated | Source Carrying!M8:N8
[23 empty] | Yes | Water | 2024-04-02 |  |  | 50.62 | Migrated Carrying Grid |  | 19_Project Management - 1426 Pleasant Garden Ln orignianl .xlsx | Migrated | Source Carrying!M9:N9
[23 empty] | Yes | Water | 2024-05-02 |  |  | 50.62 | Migrated Carrying Grid |  | 19_Project Management - 1426 Pleasant Garden Ln orignianl .xlsx | Migrated | Source Carrying!M10:N10
[23 empty] | Yes | Water | 2024-05-06 |  |  | -9.71 | Migrated Carrying Grid |  | 19_Project Management - 1426 Pleasant Garden Ln orignianl .xlsx | Migrated | Source Carrying!M11:N11
[23 empty] | Yes | Natural Gas | 2023-10-10 |  |  | 30.7 | Migrated Carrying Grid |  | 19_Project Management - 1426 Pleasant Garden Ln orignianl .xlsx | Migrated | Source Carrying!P3:Q3
[23 empty] | Yes | Natural Gas | 2023-11-07 |  |  | 10.7 | Migrated Carrying Grid |  | 19_Project Management - 1426 Pleasant Garden Ln orignianl .xlsx | Migrated | Source Carrying!P4:Q4
[23 empty] | Yes | Natural Gas | 2023-12-08 |  |  | 10.7 | Migrated Carrying Grid |  | 19_Project Management - 1426 Pleasant Garden Ln orignianl .xlsx | Migrated | Source Carrying!P5:Q5
[23 empty] | Yes | Natural Gas | 2024-01-09 |  |  | 10.7 | Migrated Carrying Grid |  | 19_Project Management - 1426 Pleasant Garden Ln orignianl .xlsx | Migrated | Source Carrying!P6:Q6
[23 empty] | Yes | Natural Gas | 2024-02-09 |  |  | 11.99 | Migrated Carrying Grid |  | 19_Project Management - 1426 Pleasant Garden Ln orignianl .xlsx | Migrated | Source Carrying!P7:Q7
[23 empty] | Yes | Natural Gas | 2024-03-08 |  |  | 11.94 | Migrated Carrying Grid |  | 19_Project Management - 1426 Pleasant Garden Ln orignianl .xlsx | Migrated | Source Carrying!P8:Q8
[23 empty] | Yes | Natural Gas | 2024-04-09 |  |  | 10.7 | Migrated Carrying Grid |  | 19_Project Management - 1426 Pleasant Garden Ln orignianl .xlsx | Migrated | Source Carrying!P9:Q9
[23 empty] | Yes | Natural Gas | 2024-05-06 |  |  | -9.71 | Migrated Carrying Grid |  | 19_Project Management - 1426 Pleasant Garden Ln orignianl .xlsx | Migrated | Source Carrying!P10:Q10
[23 empty] | Yes | HOA | 2024-06-03 |  |  | 346.23 | Migrated Carrying Grid |  | 19_Project Management - 1426 Pleasant Garden Ln orignianl .xlsx | Migrated | Source Carrying!S3:T3
[23 empty] | Yes | HOA | 2024-07-09 |  |  | 241.57 | Migrated Carrying Grid |  | 19_Project Management - 1426 Pleasant Garden Ln orignianl .xlsx | Migrated | Source Carrying!S4:T4
[23 empty] | Yes | HOA | 2025-01-13 |  |  | 253.65 | Migrated Carrying Grid |  | 19_Project Management - 1426 Pleasant Garden Ln orignianl .xlsx | Migrated | Source Carrying!S5:T5
[23 empty] | Yes | HOA | 2025-05-15 |  |  | 25 | Migrated Carrying Grid |  | 19_Project Management - 1426 Pleasant Garden Ln orignianl .xlsx | Migrated | Source Carrying!S6:T6
[23 empty] | Yes | HOA | 2025-07-16 |  |  | 253.65 | Migrated Carrying Grid |  | 19_Project Management - 1426 Pleasant Garden Ln orignianl .xlsx | Migrated | Source Carrying!S7:T7
[23 empty] | Yes | HOA | 2026-01-15 |  |  | 253.65 | Migrated Carrying Grid |  | 19_Project Management - 1426 Pleasant Garden Ln orignianl .xlsx | Migrated | Source Carrying!S8:T8
[23 empty] | Yes | HOA | 2025-06-30 |  |  | 0 | Migrated Carrying Grid |  | 19_Project Management - 1426 Pleasant Garden Ln orignianl .xlsx | Migrated | Source Carrying!S13:T13
[23 empty] | Yes | HOA | 2025-12-27 |  |  | 0 | Migrated Carrying Grid |  | 19_Project Management - 1426 Pleasant Garden Ln orignianl .xlsx | Migrated | Source Carrying!S14:T14
[23 empty] | Yes | Property Taxes | 2023-11-13 |  |  | 2334.53 | Migrated Carrying Grid |  | 19_Project Management - 1426 Pleasant Garden Ln orignianl .xlsx | Migrated | Source Carrying!V3:W3
[23 empty] | Yes | Property Taxes | 2024-09-11 |  |  | 3101.83 | Migrated Carrying Grid |  | 19_Project Management - 1426 Pleasant Garden Ln orignianl .xlsx | Migrated | Source Carrying!V12:W12
[23 empty] | Yes | Property Taxes | 2025-09-11 |  |  | -3101.83 | Migrated Carrying Grid |  | 19_Project Management - 1426 Pleasant Garden Ln orignianl .xlsx | Migrated | Source Carrying!V13:W13 paid from escrow ¦ escrow offset in friendly grid

## Contract
Preassigned Rows Indicating Payment or Scheduling by Buy Your Home
Preassigned Rows Cordination of Glasgow with Contrtactors
Pasted rows from Builder's Trend Proposal
Notes: Only add rows to the bottom of the table
Cost Code | Title | Description | Qty | Unit Price
Deposit | Deposit | Initial Deposit to Start Job | 0 | 7016
Draw | Draw 1 | Draw 1 | 0 | 10505.74
Draw | Draw 2 | Draw 2 | 0 | 9940
| Sell | List with MLS | 6
HVAC | Cordinate Sub | HVAC | 0 | 0
Floor Coverings | Cordinate Sub | Flooring Contractor | 0 | 0
Supervision | Cordinate Sub | Termite Treatment | 0 | 0
Cabinets & Vanities | Cordinate Sub | Cabinet Delivery | 0 | 0
Countertops | Cordinate Sub | Manage installion of granite countertops by others in kitchen | 0 | 0
Demo | r | Kitchen countertops | 1 | 3800
Demo |  | Rug | 0
Demo |  | Vinyl flooring | 0
Paint |  | Paint Interior of houseCeiling, walls, doors, trim. Exterior2 Doors, 4 Shutters | 1 | 4950
Power Wash |  | Power wash exterior, House only | 1 | 590
Floor Coverings | LVP | Install LVP | 1 | 3790
Floor Coverings |  | All of first floor including baths and laundry room in 2nd floor. Labor and shoe mold included.
Floor Coverings |  | Note- Client will purchase flooring materials. Estimated- 850 sqft, Please include 10% for waste
Floor Coverings | Carpet | Install Carpet Estimated-884 sqft General Use Carpet and padding Labor | 1 | 1200
Countertops | Quartz | Level 1 Quartz $3,190 | 1 | 3190
Countertops | Quartz | Level 2 Quartz $3,850 | 0
Countertops | change order #9 | Level 3 Granet $4,620 | 1 | 4345
Installations | Labor and supplies | Installations | 1 | 4252.5
Installations | Labor and supplies | 3-Toilets | 1
Installations | Labor and supplies | 1-Kitchen Sink | 1
Installations | Labor and supplies | 1-Shower doors | 1
Installations | Labor and supplies | 2- Mirrors | 1
Installations | Labor and supplies | 1- Stove, | 1
Installations | Labor and supplies | Dish Washer | 1
Installations | Labor and supplies | Microwave | 1
Installations | Labor and supplies | 2- TP Holders | 1
Installations | Labor and supplies | 2- Ceiling Fans | 1
Installations | Labor and supplies | 2- Kitchen light fixtures | 1
Installations | Labor and supplies | 1- Pantry Light | 1
Installations | Labor and supplies | 2- Shower heads | 1
Installations | Labor and supplies | Drywall Repair in garage Labor and supplies included | 1
Installations | change order #1 | Fix Screens | 1 | 600
Floor Coverings | change order #2 | Carpet Purchase | 1 | 1800
Floor Coverings | change order #3 | program remote for LR fan | 1 | 50
Installations | change order #4 | replace half bath mirror | 1 | 75
Installations | change order #5 | repair vinyl corner piece on back of house | 1 | 75
Floor Coverings | change order #6 | Purchase LVP | 1 | 2980.24
Paint | change order #7 | 2 gal primer, 10 ceiling Paint | 1 | 294
Installations | change order #8 | credit cost for pantry light installation(item 33) | 1 | -125
Countertops | change order #9 | credit Level 1 Quartz $3,190 | 1 | -3190
Installations | change order #10 | credit one ceiling fan installation (not needed) | 1 | 0
Installations | change order #11 | credit one kitchen light fixture installation (item 32) | 1 | -125
Installations | change order #12 | credit 2 TP holders installation | 1 | -50
Installations | change order #13 | Install hall bath accessories | 1 | 75
Installations | change order #14 | Install doorbell | 1 | 75
Installations | change order #15 | Install mailbox (duplicates CO24 | 1 | 0
Installations | change order #16 | Install can light front porch (appears as duplicate to 27) | 0 | 125
Installations | change order #17 | Install outlet cover front porch | 1 | 50
Installations | change order #18 | Hall bath vanity hinge and hardware | 1 | 50
Installations | change order #19 | Replace one fence board | 1 | 50
Exterior | change order #20 | Power wash exterior patio, front walk, driveway | 1 | 75
Installations | change order #21 | Install 3 door stops | 1 | 50
Exterior | change order #22 | Repair door rot front and back | 1 | 150
Painting | change order #23 | Paint mailbox post white | 1 | 75
Exterior | change order #24 | Replace mailbox (duplicates CO15) | 1 | 50
Cleaning | change order #25 | Final cleaning (not needed) | 1 | 0
Installations | change order #26 | light bulbs and replacment | 1 | 75
Installations | change order #27 | Fix new can light front door (duplicates CO16) | 1 | 200
Installations | change order #28 | Bath faucets inspection (why) | 1 | 50
Installations | change order #29 | Gutters | 1 | 100
Installations | change order #30 | Clogged Plumbing | 1 | 150
Installations | change order #31 | Gas Fireplace | 1 | 75
Installations | change order #32 | Replace foyer glass | 1 | 797.37
Installations | change order #33 | Remove stickons from cabinet doors | 1 | 50
Draw | Draw 3 | Draw 3 | 0 | 2990
Installations | change order #34 | Install door knobs in second fl vanity | 1 | 50
Installations | change order #35 | Install smoke detectors 5 smoke detectors $75 each = $375 | 1 | 375
Installations | change order #36 | House numbers installation | 1 | 50
Draw | Draw 4 | Draw 4 | 0 | 1322.37

## UpdateContract
These Cells are updated from the Proposal tab and are protected here. | [7 empty] | These cells are updated here and carried over to the Gnatt Chart | [5 empty] | Contracted Task | 1 | Payment | 4
[14 empty] | Change Order | 2 | Not Used | 0
[14 empty] | Manage Vendor | 3 | Post Contract | 5
Party | Item | Cost Code | Title | Description | Qty | Unit Price | Price | Done | Group Order | Start Date | Days | Paid | Notes
AvilaCRI | 1 | Deposit | Deposit | Initial Deposit to Start Job | 0 | 7016 | 0 | Yes | 4 | 2023-10-13 |  | 7016
AvilaCRI | 2 | Draw | Draw 1 | Draw 1 | 0 | 10505.74 | 0 | yes | 4 | 2023-10-19 |  | 10505.74
AvilaCRI | 3 | Draw | Draw 2 | Draw 2 | 0 | 9940 | 0 | Yes | 4 | 2023-10-27 |  | 9940
| 4 |  | Sell | List with MLS | 6 |  |  |  | 5
AvilaCRI | 5 | HVAC | Cordinate Sub | HVAC | 0 | 0 | 0 | Yes | 0
AvilaCRI | 6 | Floor Coverings | Cordinate Sub | Flooring Contractor | 0 | 0 | 0 | Yes | 0 |  | 5
AvilaCRI | 7 | Supervision | Cordinate Sub | Termite Treatment | 0 | 0 | 0 | Yes | 0
AvilaCRI | 8 | Cabinets & Vanities | Cordinate Sub | Cabinet Delivery | 0 | 0 | 0 | Yes | 0
AvilaCRI | 9 | Countertops | Cordinate Sub | Manage installion of granite countertops by others in kitchen | 0 | 0 | 0 | yes | 0
AvilaCRI | 10 | Demo | r | Kitchen countertops | 1 | 3800 | 3800 | yes | 1 | 2023-10-14 | 1
AvilaCRI | 11 | Demo |  | Rug | 0 |  |  | yes | 1 | 2023-10-14 | 1
AvilaCRI | 12 | Demo |  | Vinyl flooring | 0 |  |  | yes | 1 | 2023-10-14 | 1
AvilaCRI | 13 | Paint |  | Paint Interior of houseCeiling, walls, doors, trim. Exterior2 Doors, 4 Shutters | 1 | 4950 | 4950 | yes | 1 | 2023-10-17 | 7
AvilaCRI | 14 | Power Wash |  | Power wash exterior, House only | 1 | 590 | 590 | Yes | 1 |  | 1
AvilaCRI | 15 | Floor Coverings | LVP | Install LVP | 1 | 3790 | 3790 | Yes | 1 | 2023-10-27 | 2
AvilaCRI | 16 | Floor Coverings |  | All of first floor including baths and laundry room in 2nd floor. Labor and shoe mold included. |  |  |  | Yes | 1
AvilaCRI | 17 | Floor Coverings |  | Note- Client will purchase flooring materials. Estimated- 850 sqft, Please include 10% for waste |  |  |  | Yes | 1
AvilaCRI | 18 | Floor Coverings | Carpet | Install Carpet Estimated-884 sqft General Use Carpet and padding Labor | 1 | 1200 | 1200 | yes | 1 | 2023-10-26 | 1
AvilaCRI | 19 | Countertops | Quartz | Level 1 Quartz $3,190 | 1 | 3190 | 3190 | yes | 1 | 2023-10-20 | 1 |  | credit via CO#9
AvilaCRI | 20 | Countertops | Quartz | Level 2 Quartz $3,850 | 0 |  |  | Yes | 1 | 2023-10-20
AvilaCRI | 21 | Countertops | change order #9 | Level 3 Granet $4,620 | 1 | 4345 | 4345 | yes | 2 | 2023-10-20
AvilaCRI | 22 | Installations | Labor and supplies | Installations | 1 | 4252.5 | 4252.5 | yes | 1 | 2023-10-30 | 7
AvilaCRI | 23 | Installations | Labor and supplies | 3-Toilets | 1 |  |  | Yes | 1 | 2023-10-30
AvilaCRI | 24 | Installations | Labor and supplies | 1-Kitchen Sink | 1 |  |  | Yes | 1 | 2023-10-30
AvilaCRI | 25 | Installations | Labor and supplies | 1-Shower doors | 1 |  |  | Yes | 1 | 2023-10-30
AvilaCRI | 26 | Installations | Labor and supplies | 2- Mirrors | 1 |  |  | Yes | 1 | 2023-10-30
AvilaCRI | 27 | Installations | Labor and supplies | 1- Stove, | 1 |  |  | Yes | 1 | 2023-10-30
AvilaCRI | 28 | Installations | Labor and supplies | Dish Washer | 1 |  |  | Yes | 1 | 2023-10-30
AvilaCRI | 29 | Installations | Labor and supplies | Microwave | 1 |  |  | Yes | 1 | 2023-10-30
AvilaCRI | 30 | Installations | Labor and supplies | 2- TP Holders | 1 |  |  | Yes | 1 | 2023-10-30
AvilaCRI | 31 | Installations | Labor and supplies | 2- Ceiling Fans | 1 |  |  | Yes | 1 | 2023-10-30
AvilaCRI | 32 | Installations | Labor and supplies | 2- Kitchen light fixtures | 1 |  |  | Yes | 1 | 2023-10-30
AvilaCRI | 33 | Installations | Labor and supplies | 1- Pantry Light | 1 |  |  | Yes | 1 | 2023-10-30
AvilaCRI | 34 | Installations | Labor and supplies | 2- Shower heads | 1 |  |  | Yes | 1 | 2023-10-30
AvilaCRI | 35 | Installations | Labor and supplies | Drywall Repair in garage Labor and supplies included | 1 |  |  | Yes | 1 | 2023-10-17 | 1
AvilaCRI | 36 | Installations | change order #1 | Fix Screens | 1 | 600 | 600 | Yes | 2 |  |  |  | yes
AvilaCRI | 37 | Floor Coverings | change order #2 | Carpet Purchase | 1 | 1800 | 1800 | yes | 2 | 2023-10-19 |  |  | yes
AvilaCRI | 38 | Floor Coverings | change order #3 | program remote for LR fan | 1 | 50 | 50 | Yes | 2
AvilaCRI | 39 | Installations | change order #4 | replace half bath mirror | 1 | 75 | 75 | Yes | 2 | 2023-11-03 |  |  | yes
AvilaCRI | 40 | Installations | change order #5 | repair vinyl corner piece on back of house | 1 | 75 | 75 | Yes | 2 | 2023-10-27 |  |  | yes
AvilaCRI | 41 | Floor Coverings | change order #6 | Purchase LVP | 1 | 2980.24 | 2980.24 | yes | 2 | 2023-10-19 |  |  | yes
AvilaCRI | 42 | Paint | change order #7 | 2 gal primer, 10 ceiling Paint | 1 | 294 | 294 | Yes | 2 | 2023-10-27 |  |  | yes
AvilaCRI | 43 | Installations | change order #8 | credit cost for pantry light installation(item 33) | 1 | -125 | -125 | Yes | 2 | 2023-11-03 |  |  | yes
AvilaCRI | 44 | Countertops | change order #9 | credit Level 1 Quartz $3,190 | 1 | -3190 | -3190 | yes | 2 | 2023-10-20 |  |  | yes
AvilaCRI | 45 | Installations | change order #10 | credit one ceiling fan installation (not needed) | 1 | 0 | 0 |  | 2
AvilaCRI | 46 | Installations | change order #11 | credit one kitchen light fixture installation (item 32) | 1 | -125 | -125 | yes | 2 | 2023-11-03 |  |  | yes
AvilaCRI | 47 | Installations | change order #12 | credit 2 TP holders installation | 1 | -50 | -50 | Yes | 2 |  |  |  | yes
AvilaCRI | 48 | Installations | change order #13 | Install hall bath accessories | 1 | 75 | 75 | Yes | 2 | 2023-11-03 |  |  | yes
AvilaCRI | 49 | Installations | change order #14 | Install doorbell | 1 | 75 | 75 | Yes | 2 | 2023-11-03 |  |  | yes
AvilaCRI | 50 | Installations | change order #15 | Install mailbox (duplicates CO24 | 1 | 0 | 0 |  | 2
AvilaCRI | 51 | Installations | change order #16 | Install can light front porch (appears as duplicate to 27) | 0 | 125 | 0 |  | 2 | 2023-11-03
AvilaCRI | 52 | Installations | change order #17 | Install outlet cover front porch | 1 | 50 | 50 | Yes | 2 | 2023-11-03 |  |  | yes
AvilaCRI | 53 | Installations | change order #18 | Hall bath vanity hinge and hardware | 1 | 50 | 50 | Yes | 2 |  |  |  | yes
AvilaCRI | 54 | Installations | change order #19 | Replace one fence board | 1 | 50 | 50 | Yes | 2 | 2023-11-03 |  |  | yes
AvilaCRI | 55 | Exterior | change order #20 | Power wash exterior patio, front walk, driveway | 1 | 75 | 75 | Yes | 2 | 2023-11-03 |  |  | yes
AvilaCRI | 56 | Installations | change order #21 | Install 3 door stops | 1 | 50 | 50 | Yes | 2 | 2023-11-03 |  |  | yes
AvilaCRI | 57 | Exterior | change order #22 | Repair door rot front and back | 1 | 150 | 150 | Yes | 2 | 2023-11-03 |  |  | yes
AvilaCRI | 58 | Painting | change order #23 | Paint mailbox post white | 1 | 75 | 75 | Yes | 2 | 2023-11-03 |  |  | yes
AvilaCRI | 59 | Exterior | change order #24 | Replace mailbox (duplicates CO15) | 1 | 50 | 50 | Yes | 2 | 2023-11-03
AvilaCRI | 60 | Cleaning | change order #25 | Final cleaning (not needed) | 1 | 0 | 0 |  | 2
AvilaCRI | 61 | Installations | change order #26 | light bulbs and replacment | 1 | 75 | 75 | Yes | 2 | 2023-11-03 |  |  | yes
AvilaCRI | 62 | Installations | change order #27 | Fix new can light front door (duplicates CO16) | 1 | 200 | 200 | yes | 2 | 2023-11-03 |  |  | yes
AvilaCRI | 63 | Installations | change order #28 | Bath faucets inspection (why) | 1 | 50 | 50 | yes | 2 | 2023-11-03
AvilaCRI | 64 | Installations | change order #29 | Gutters | 1 | 100 | 100 | Yes | 2 | 2023-11-03 |  |  | yes
AvilaCRI | 65 | Installations | change order #30 | Clogged Plumbing | 1 | 150 | 150 | Yes | 2 | 2023-11-03 |  |  | yes
AvilaCRI | 66 | Installations | change order #31 | Gas Fireplace | 1 | 75 | 75 | Yes | 2 |  |  |  | yes
AvilaCRI | 67 | Installations | change order #32 | Replace foyer glass | 1 | 797.37 | 797.37 | Yes | 2
AvilaCRI | 68 | Installations | change order #33 | Remove stickons from cabinet doors | 1 | 50 | 50 | Yes | 2 |  |  |  | yes
AvilaCRI | 69 | Draw | Draw 3 | Draw 3 | 0 | 2990 | 0 | Yes | 4 | 2023-11-07 |  | 2900 | yes
AvilaCRI | 70 | Installations | change order #34 | Install door knobs in second fl vanity | 1 | 50 | 50 | Yes | 2 |  |  |  | yes
AvilaCRI | 71 | Installations | change order #35 | Install smoke detectors 5 smoke detectors $75 each = $375 | 1 | 375 | 375 | Yes | 2 |  |  |  | yes
AvilaCRI | 72 | Installations | change order #36 | House numbers installation | 1 | 50 | 50 | Yes | 2 |  |  |  | yes
AvilaCRI | 73 | Draw | Draw 4 | Draw 4 | 0 | 1322.37 | 0 | Yes | 4 | 2029-11-23 |  | 1322.37 | yes

## Gnatt Chart
[9 empty] | Expense |  |  | Due |  | ToDo
AvilaCRI |  | Buy Your Home |  | Project Start Date: | 2023-10-13 |  | Company Paid Materials Total: |  | 16237.9463 |  |  | 3068.7963 |  | 9673.7963
[7 empty] | Contractors Total: |  | 0 |  |  | 0 |  | 0
1426 Pleasant Garden Ln, Raleigh, NC 27604 | 1426 Pleasant Garden Ln, Raleigh, NC 27604 |  |  | Milestone Marker: |  | 1 | AvilaCRI Total: |  | 31174.11 |  |  | -510 |  | -510
| Cells H5 through BK5 contain the day number of the month for the Month represented in the cell block above each date cell and are auto calculated. Do not modify these cells. Dates leading up to Today are shaded. |  |  | Milestone Marker 2: |  | 2 | Grand Total |  | 47412.0563 |  |  | 2558.7963 |  | 9163.7963
Buy Your Home Supplied Materials
Assigned | Item # | Cost Code | Title | Description | Qty | Unit Price | Price | Done | Group Order | Start Date | Days | Paid | Due | Notes
Buy Your Home | 1 |  |  | Cleanup (from Demo & Trash Haul Tab) | 1 | 0 | 0 | yes |  |  |  | 1623.75 | 0
Buy Your Home | 2 |  |  | Taxes - outside of closing (from Taxes tab) | 0 | 0 | 0 | [5 empty] | 0
Buy Your Home | 2 |  |  | Appliances (from Appliances Tab) | 1 | 1740.4502 | 1740.4502 | yes |  |  |  | 1725.47 | 1740.4502
Buy Your Home | 3 |  |  | Plubing Fixtures | 1 | 1279.5461 | 1279.5461 | yes |  |  |  | 706.39 | 1279.5461
Buy Your Home | 4 |  |  | Windows & Doors | 0 | 2024.31 | 0 | [5 empty] | 0
Buy Your Home | 5 |  |  | Cabinets (from Cabinets Tab) | 0 | 4165 | 0 | [5 empty] | 0
Buy Your Home | 6 |  |  | Paint (from Paint Tab) | 1 | 5750 | 5750 | yes |  |  |  | 1788.82 | 5750
Buy Your Home | 7 |  |  | Flooring | 1 | 6605 | 6605 | [5 empty] | 0
Buy Your Home | 8 |  |  | Electrical fixtures (from Misc Tab) | 1 | 581.91 | 581.91 | yes |  |  |  | 568.65 | 581.91
Buy Your Home | 9 |  |  | Exterior Tab | 1 | 71.04 | 71.04 | yes |  |  |  | 61.07 | 71.04
Buy Your Home | 10 |  |  | Landscaping Tab | 1 | 210 | 210 | yes |  |  |  | 90 | 210
Buy Your Home | 11 |  |  | HVAC Contractor | 0 | 0 | 0 | [5 empty] | 0
Buy Your Home | 12 |  |  | Landscape | 0 | 0 | 0 | [5 empty] | 0
Buy Your Home | 13 |  |  | Exterior- Termite | 0 | 0 | 0 | [5 empty] | 0
Buy Your Home | 14 |  |  | Drainage | 0 | 0 | 0 | [5 empty] | 0
Buy Your Home's Paid Contractors
Mabrey Roofing | 15 |  |  | Roof Contractor | 1 | 0 | 0 | [5 empty] | 0 | [12 empty] | Scrolling Increment:
Mabrey Roofing | 16 |  |  | Roof Contractor | 0 | 400 | 0 | [5 empty] | 0
Love Services | 17 |  |  | HVAC Contractor - Package Heat Pump | 0 | 9504.5 | 0 | [5 empty] | 0 | [13 empty] | 0
Love Services | 18 |  |  | HVAC Contractor - Duct Work | 0 | 4598 | 0 | [5 empty] | 0
|  |  |  | AvilaCRI Items (all items should be updated from Proposal or ProposalUpdate tab) | [29 empty] | November | [29 empty] | December | [30 empty] | January
Party | Item | Cost Code | Title | Description | Qty | Unit Price | Price | Done | Group Order | Start Date | Days | Paid | Due | Notes | 2023-10-13 | 2023-10-14 | 2023-10-15 | 2023-10-16 | 2023-10-17 | 2023-10-18 | 2023-10-19 | 2023-10-20 | 2023-10-21 | 2023-10-22 | 2023-10-23 | 2023-10-24 | 2023-10-25 | 2023-10-26 | 2023-10-27 | 2023-10-28 | 2023-10-29 | 2023-10-30 | 2023-10-31 | 2023-11-01 | 2023-11-02 | 2023-11-03 | 2023-11-04 | 2023-11-05 | 2023-11-06 | 2023-11-07 | 2023-11-08 | 2023-11-09 | 2023-11-10 | 2023-11-11 | 2023-11-12 | 2023-11-13 | 2023-11-14 | 2023-11-15 | 2023-11-16 | 2023-11-17 | 2023-11-18 | 2023-11-19 | 2023-11-20 | 2023-11-21 | 2023-11-22 | 2023-11-23 | 2023-11-24 | 2023-11-25 | 2023-11-26 | 2023-11-27 | 2023-11-28 | 2023-11-29 | 2023-11-30 | 2023-12-01 | 2023-12-02 | 2023-12-03 | 2023-12-04 | 2023-12-05 | 2023-12-06 | 2023-12-07 | 2023-12-08 | 2023-12-09 | 2023-12-10 | 2023-12-11 | 2023-12-12 | 2023-12-13 | 2023-12-14 | 2023-12-15 | 2023-12-16 | 2023-12-17 | 2023-12-18 | 2023-12-19 | 2023-12-20 | 2023-12-21 | 2023-12-22 | 2023-12-23 | 2023-12-24 | 2023-12-25 | 2023-12-26 | 2023-12-27 | 2023-12-28 | 2023-12-29 | 2023-12-30 | 2023-12-31 | 2024-01-01 | 2024-01-02 | 2024-01-03 | 2024-01-04
AvilaCRI | 5 | HVAC | Cordinate Sub | HVAC | 0 | 0 | 0 | Yes | 0 |  |  |  | 0
AvilaCRI | 6 | Floor Coverings | Cordinate Sub | Flooring Contractor | 0 | 0 | 0 | Yes | 0 |  | 5 |  | 0
AvilaCRI | 7 | Supervision | Cordinate Sub | Termite Treatment | 0 | 0 | 0 | Yes | 0 |  |  |  | 0
AvilaCRI | 8 | Cabinets & Vanities | Cordinate Sub | Cabinet Delivery | 0 | 0 | 0 | Yes | 0 |  |  |  | 0
AvilaCRI | 9 | Countertops | Cordinate Sub | Manage installion of granite countertops by others in kitchen | 0 | 0 | 0 | yes | 0 |  |  |  | 0
AvilaCRI | 10 | Demo | r | Kitchen countertops | 1 | 3800 | 3800 | yes | 1 | 2023-10-14 | 1 |  | 3800 |  |  | 1
AvilaCRI | 11 | Demo |  | Rug | 0 |  |  | yes | 1 | 2023-10-14 | 1 |  |  |  |  | 1
AvilaCRI | 12 | Demo |  | Vinyl flooring | 0 |  |  | yes | 1 | 2023-10-14 | 1 |  |  |  |  | 1
AvilaCRI | 13 | Paint |  | Paint Interior of houseCeiling, walls, doors, trim. Exterior2 Doors, 4 Shutters | 1 | 4950 | 4950 | yes | 1 | 2023-10-17 | 7 |  | 4950 | [5 empty] | 1 | 2 | 2 | 2 | 2 | 2 | 2
AvilaCRI | 35 | Installations | Labor and supplies | Drywall Repair in garage Labor and supplies included | 1 |  |  | Yes | 1 | 2023-10-17 | 1 | [7 empty] | 1
AvilaCRI | 19 | Countertops | Quartz | Level 1 Quartz $3,190 | 1 | 3190 | 3190 | yes | 1 | 2023-10-20 | 1 |  | 3190 | credit via CO#9 | [7 empty] | 1
AvilaCRI | 20 | Countertops | Quartz | Level 2 Quartz $3,850 | 0 |  |  | Yes | 1 | 2023-10-20 | [11 empty] | 1
AvilaCRI | 18 | Floor Coverings | Carpet | Install Carpet Estimated-884 sqft General Use Carpet and padding Labor | 1 | 1200 | 1200 | yes | 1 | 2023-10-26 | 1 |  | 1200 | [14 empty] | 1
AvilaCRI | 15 | Floor Coverings | LVP | Install LVP | 1 | 3790 | 3790 | Yes | 1 | 2023-10-27 | 2 |  | 3790 | [15 empty] | 1 | 2
AvilaCRI | 22 | Installations | Labor and supplies | Installations | 1 | 4252.5 | 4252.5 | yes | 1 | 2023-10-30 | 7 |  | 4252.5 | [18 empty] | 1 | 2 | 2 | 2 | 2 | 2 | 2
AvilaCRI | 23 | Installations | Labor and supplies | 3-Toilets | 1 |  |  | Yes | 1 | 2023-10-30 | [21 empty] | 1
AvilaCRI | 24 | Installations | Labor and supplies | 1-Kitchen Sink | 1 |  |  | Yes | 1 | 2023-10-30 | [21 empty] | 1
AvilaCRI | 25 | Installations | Labor and supplies | 1-Shower doors | 1 |  |  | Yes | 1 | 2023-10-30 | [21 empty] | 1
AvilaCRI | 26 | Installations | Labor and supplies | 2- Mirrors | 1 |  |  | Yes | 1 | 2023-10-30 | [21 empty] | 1
AvilaCRI | 27 | Installations | Labor and supplies | 1- Stove, | 1 |  |  | Yes | 1 | 2023-10-30 | [21 empty] | 1
AvilaCRI | 28 | Installations | Labor and supplies | Dish Washer | 1 |  |  | Yes | 1 | 2023-10-30 | [21 empty] | 1
AvilaCRI | 29 | Installations | Labor and supplies | Microwave | 1 |  |  | Yes | 1 | 2023-10-30 | [21 empty] | 1
AvilaCRI | 30 | Installations | Labor and supplies | 2- TP Holders | 1 |  |  | Yes | 1 | 2023-10-30 | [21 empty] | 1
AvilaCRI | 31 | Installations | Labor and supplies | 2- Ceiling Fans | 1 |  |  | Yes | 1 | 2023-10-30 | [21 empty] | 1
AvilaCRI | 32 | Installations | Labor and supplies | 2- Kitchen light fixtures | 1 |  |  | Yes | 1 | 2023-10-30 | [21 empty] | 1
AvilaCRI | 33 | Installations | Labor and supplies | 1- Pantry Light | 1 |  |  | Yes | 1 | 2023-10-30 | [21 empty] | 1
AvilaCRI | 34 | Installations | Labor and supplies | 2- Shower heads | 1 |  |  | Yes | 1 | 2023-10-30 | [21 empty] | 1
AvilaCRI | 14 | Power Wash |  | Power wash exterior, House only | 1 | 590 | 590 | Yes | 1 |  | 1 |  | 590
AvilaCRI | 16 | Floor Coverings |  | All of first floor including baths and laundry room in 2nd floor. Labor and shoe mold included. |  |  |  | Yes | 1
AvilaCRI | 17 | Floor Coverings |  | Note- Client will purchase flooring materials. Estimated- 850 sqft, Please include 10% for waste |  |  |  | Yes | 1
AvilaCRI | 37 | Floor Coverings | change order #2 | Carpet Purchase | 1 | 1800 | 1800 | yes | 2 | 2023-10-19 |  |  | 1800 | yes | [6 empty] | 1
AvilaCRI | 41 | Floor Coverings | change order #6 | Purchase LVP | 1 | 2980.24 | 2980.24 | yes | 2 | 2023-10-19 |  |  | 2980.24 | yes | [6 empty] | 1
AvilaCRI | 21 | Countertops | change order #9 | Level 3 Granet $4,620 | 1 | 4345 | 4345 | yes | 2 | 2023-10-20 |  |  | 4345 | [8 empty] | 1
AvilaCRI | 44 | Countertops | change order #9 | credit Level 1 Quartz $3,190 | 1 | -3190 | -3190 | yes | 2 | 2023-10-20 |  |  | -3190 | yes | [7 empty] | 1
AvilaCRI | 40 | Installations | change order #5 | repair vinyl corner piece on back of house | 1 | 75 | 75 | Yes | 2 | 2023-10-27 |  |  | 75 | yes | [14 empty] | 1
AvilaCRI | 42 | Paint | change order #7 | 2 gal primer, 10 ceiling Paint | 1 | 294 | 294 | Yes | 2 | 2023-10-27 |  |  | 294 | yes | [14 empty] | 1
AvilaCRI | 39 | Installations | change order #4 | replace half bath mirror | 1 | 75 | 75 | Yes | 2 | 2023-11-03 |  |  | 75 | yes | [21 empty] | 1
AvilaCRI | 43 | Installations | change order #8 | credit cost for pantry light installation(item 33) | 1 | -125 | -125 | Yes | 2 | 2023-11-03 |  |  | -125 | yes | [21 empty] | 1
AvilaCRI | 46 | Installations | change order #11 | credit one kitchen light fixture installation (item 32) | 1 | -125 | -125 | yes | 2 | 2023-11-03 |  |  | -125 | yes | [21 empty] | 1
AvilaCRI | 48 | Installations | change order #13 | Install hall bath accessories | 1 | 75 | 75 | Yes | 2 | 2023-11-03 |  |  | 75 | yes | [21 empty] | 1
AvilaCRI | 49 | Installations | change order #14 | Install doorbell | 1 | 75 | 75 | Yes | 2 | 2023-11-03 |  |  | 75 | yes | [21 empty] | 1
AvilaCRI | 51 | Installations | change order #16 | Install can light front porch (appears as duplicate to 27) | 0 | 125 | 0 |  | 2 | 2023-11-03 | [25 empty] | 1
AvilaCRI | 52 | Installations | change order #17 | Install outlet cover front porch | 1 | 50 | 50 | Yes | 2 | 2023-11-03 |  |  | 50 | yes | [21 empty] | 1
AvilaCRI | 54 | Installations | change order #19 | Replace one fence board | 1 | 50 | 50 | Yes | 2 | 2023-11-03 |  |  | 50 | yes | [21 empty] | 1
AvilaCRI | 55 | Exterior | change order #20 | Power wash exterior patio, front walk, driveway | 1 | 75 | 75 | Yes | 2 | 2023-11-03 |  |  | 75 | yes | [21 empty] | 1
AvilaCRI | 56 | Installations | change order #21 | Install 3 door stops | 1 | 50 | 50 | Yes | 2 | 2023-11-03 |  |  | 50 | yes | [21 empty] | 1
AvilaCRI | 57 | Exterior | change order #22 | Repair door rot front and back | 1 | 150 | 150 | Yes | 2 | 2023-11-03 |  |  | 150 | yes | [21 empty] | 1
AvilaCRI | 58 | Painting | change order #23 | Paint mailbox post white | 1 | 75 | 75 | Yes | 2 | 2023-11-03 |  |  | 75 | yes | [21 empty] | 1
AvilaCRI | 59 | Exterior | change order #24 | Replace mailbox (duplicates CO15) | 1 | 50 | 50 | Yes | 2 | 2023-11-03 |  |  | 50 | [22 empty] | 1
AvilaCRI | 61 | Installations | change order #26 | light bulbs and replacment | 1 | 75 | 75 | Yes | 2 | 2023-11-03 |  |  | 75 | yes | [21 empty] | 1
AvilaCRI | 62 | Installations | change order #27 | Fix new can light front door (duplicates CO16) | 1 | 200 | 200 | yes | 2 | 2023-11-03 |  |  | 200 | yes | [21 empty] | 1
AvilaCRI | 63 | Installations | change order #28 | Bath faucets inspection (why) | 1 | 50 | 50 | yes | 2 | 2023-11-03 |  |  | 50 | [22 empty] | 1
AvilaCRI | 64 | Installations | change order #29 | Gutters | 1 | 100 | 100 | Yes | 2 | 2023-11-03 |  |  | 100 | yes | [21 empty] | 1
AvilaCRI | 65 | Installations | change order #30 | Clogged Plumbing | 1 | 150 | 150 | Yes | 2 | 2023-11-03 |  |  | 150 | yes | [21 empty] | 1
AvilaCRI | 36 | Installations | change order #1 | Fix Screens | 1 | 600 | 600 | Yes | 2 |  |  |  | 600 | yes
AvilaCRI | 38 | Floor Coverings | change order #3 | program remote for LR fan | 1 | 50 | 50 | Yes | 2 |  |  |  | 50
AvilaCRI | 45 | Installations | change order #10 | credit one ceiling fan installation (not needed) | 1 | 0 | 0 |  | 2
AvilaCRI | 47 | Installations | change order #12 | credit 2 TP holders installation | 1 | -50 | -50 | Yes | 2 |  |  |  | -50 | yes
AvilaCRI | 50 | Installations | change order #15 | Install mailbox (duplicates CO24 | 1 | 0 | 0 |  | 2
AvilaCRI | 53 | Installations | change order #18 | Hall bath vanity hinge and hardware | 1 | 50 | 50 | Yes | 2 |  |  |  | 50 | yes
AvilaCRI | 60 | Cleaning | change order #25 | Final cleaning (not needed) | 1 | 0 | 0 |  | 2
AvilaCRI | 66 | Installations | change order #31 | Gas Fireplace | 1 | 75 | 75 | Yes | 2 |  |  |  | 75 | yes
AvilaCRI | 67 | Installations | change order #32 | Replace foyer glass | 1 | 797.37 | 797.37 | Yes | 2 |  |  |  | 797.37
AvilaCRI | 68 | Installations | change order #33 | Remove stickons from cabinet doors | 1 | 50 | 50 | Yes | 2 |  |  |  | 50 | yes
AvilaCRI | 70 | Installations | change order #34 | Install door knobs in second fl vanity | 1 | 50 | 50 | Yes | 2 |  |  |  | 50 | yes
AvilaCRI | 71 | Installations | change order #35 | Install smoke detectors 5 smoke detectors $75 each = $375 | 1 | 375 | 375 | Yes | 2 |  |  |  | 375 | yes
AvilaCRI | 72 | Installations | change order #36 | House numbers installation | 1 | 50 | 50 | Yes | 2 |  |  |  | 50 | yes
AvilaCRI | 1 | Deposit | Deposit | Initial Deposit to Start Job | 0 | 7016 | 0 | Yes | 4 | 2023-10-13 |  | 7016 | 0
AvilaCRI | 2 | Draw | Draw 1 | Draw 1 | 0 | 10505.74 | 0 | yes | 4 | 2023-10-19 |  | 10505.74 | 0
AvilaCRI | 3 | Draw | Draw 2 | Draw 2 | 0 | 9940 | 0 | Yes | 4 | 2023-10-27 |  | 9940 | 0
AvilaCRI | 69 | Draw | Draw 3 | Draw 3 | 0 | 2990 | 0 | Yes | 4 | 2023-11-07 |  | 2900 | 0 | yes
AvilaCRI | 73 | Draw | Draw 4 | Draw 4 | 0 | 1322.37 | 0 | Yes | 4 | 2029-11-23 |  | 1322.37 | 0 | yes
| 4 |  | Sell | List with MLS | 6 |  |  |  | 5

## Recap
Only undone Gnatt Chart Items are in this list | [6 empty] | Edit these Entries. Must manually add a matching Item # |  |  |  | Do not edit contents here - Edit in Orange, Recap Table
Do not edit contents here - Edit on Proposal Update Tab | [6 empty] | Recap Table - Add Recap Items here |  |  |  | Recap Summary Table - 1426 Pleasant Garden Ln, Raleigh, NC 27604
Item | Title | Description | Order | Start Date | Price | Done | Item | Comment | Date | Done | Item | Title | Description | Comment | Date | Done
45 | change order #10 | credit one ceiling fan installation (not needed) | 2 |  | 0 |  | 15 | Pick floor sample | 2023-10-18 | yes | 51 | change order #16 | Install can light front porch (appears as duplicate to 27) | item 62, CO16 & CO17 are the same CO w/ different prices | 2023-11-07
50 | change order #15 | Install mailbox (duplicates CO24 | 2 |  | 0 |  | 31 | Left Remote for LR fan | 2023-10-18 | yes
60 | change order #25 | Final cleaning (not needed) | 2 |  | 0 |  | 23 | We will get toilets by 10/25 | 2023-10-18 | yes
51 | change order #16 | Install can light front porch (appears as duplicate to 27) | 2 | 2023-11-03 | 0 |  | 50 | Price CO16 | 2023-10-24 | yes
4 | Sell | List with MLS | 5 |  |  |  | 53 | Price CO19 | 2023-10-24 | yes
[7 empty] | 54 | Price CO20 | 2023-10-24 | yes
[7 empty] | 55 | Price CO21 | 2023-10-24 | yes
[7 empty] | 56 | Price CO22 | 2023-10-24 | yes
[7 empty] | 57 | Price CO23 | 2023-10-24 | yes
[7 empty] | 58 | Price CO24 | 2023-10-24 | yes
[7 empty] | 59 | Price CO25 | 2023-10-24 | yes
[7 empty] | 60 | Price CO26 | 2023-10-24 | yes
[7 empty] | 67 | Add start dates | 2023-11-07
[7 empty] | 59 | HO add numbers on mailbox? | 2023-11-07
[8 empty] | Call garage door repair | 2023-11-07
[7 empty] | 48 | Is this a duplicate of 39, CO4 & 13 | 2023-11-07
[7 empty] | 51 | item 62, CO16 & CO17 are the same CO w/ different prices | 2023-11-07
[7 empty] | 63 | What is this? | 2023-11-07
[7 empty] | 65 | What plumbing clog clearing | 2023-11-07
[7 empty] | 66 | needs date, cost | 2023-11-07
[7 empty] | 53 | needs price and scope | 2023-11-07
[7 empty] | 25 | Not needed | 2023-11-07 | yes
[7 empty] | 36 | is this done? | 2023-11-07
[7 empty] | 38 | Need a price | 2023-11-07
[7 empty] | 25 | Is this done? | 2023-11-07
[7 empty] | 14 | is this done? | 2023-11-07
[7 empty] | 68 | Price new change order | 2023-11-07
[7 empty] | 62 | Duplicates?

## Taxes
This is for taxes paid, outside of closing process
Gov't Entity | Date | Tax Event | Tax
Wake County | 19-22 | Property Transfer Tax | 0
0

## Seller Advance
Misc Cost | AdvancesReduce Seller Pauout
Sellers Payout
Sellers Payoff | 0 | 0
Seller Incentive/Day: | 33
Seller Vacate Days Early: | 0 | 0
|  | Total Cost | 0
|  |  | Total Owed: | 0

## MISC
Misc
| Item Name | Quanity | Cost/Unit | Sub-Total | Tax | Total
Living Room Ceiling Fan |  | 0 | 0 | 0 | 0
Bedroom Ceiling Fan |  | 0 | 0 | 0 | 0
Ceiling Fan Pole |  | 0 | 0 | 0 | 0
Kitchen Light Fixture |  | 0 | 0 | 0 | 0
Dining Room Light Fixture |  | 0 | 0 | 0 | 0
Over Kitchen Sink Light Fixture |  | 0 | 0 | 0 | 0
Hall Light Fixture |  | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0
Hall Bath Light Fixture |  | 0 | 0 | 0 | 0
Master Bath Light Fixture |  | 0 | 0 | 0 | 0
1/2 Bath Light Fixture |  | 0 | 0 | 0 | 0
Bedroom Light Fixture |  | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0
Laundry Light Fixture |  | 0 | 0 | 0 | 0
Closet Light Fixture |  | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0
Exterior Light Fixture |  | 0 | 0 | 0 | 0
Exterior Motion Light Fixture |  | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0
Bulbs |  | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0
Kitchen Sink Faucet |  | 0 | 0 | 0 | 0
Bathroom Sink Faucet |  | 0 | 0 | 0 | 0
Toilet |  | 0 | 0 | 0 | 0
Shower Head |  | 0 | 0 | 0 | 0
Shower Handle |  | 0 | 0 | 0 | 0
Tub Faucet |  | 0 | 0 | 0 | 0
Shower Kit |  | 0 | 0 | 0 | 0
Tub |  | 0 | 0 | 0 | 0
Washing Machine Outlet |  | 0 | 0 | 0 | 0
Dryer Vent |  | 0 | 0 | 0 | 0
Kitchen Disposal |  | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0
Hall Bath Vanity |  | 0 | 0 | 0 | 0
1/2 Bath Vanity |  | 0 | 0 | 0 | 0
Master Bath Vanity |  | 0 | 0 | 0 | 0
Bath Sink Top |  | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0
Mirror |  | 0 | 0 | 0 | 0
Shower door |  | 0 | 0 | 0 | 0
Beveled Edge Rectangle Mirror | 6973242570225 | 2 | 49.97 | 99.94 | 7.2456
Amazon Oval Bathroom Mirror |  | 1 | 69.99 | 69.99 | 5.0743
|  | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0
Hall Bath Mirror |  | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0
|  | 0 | 0 | 0
182.2499

## Demo & Trash Haul
Vender | Date | Per Event | Iterations | Charge | Sub Total
0
Meridian | 2023-10-12 | 15 Yrd Delivery | 1 | 78.75 | 78.75
Meridian | 2023-11-03 | 15 yard Haul swap | 1 | 325 | 325
Meridian |  | C&D Disp | 0 | 104 | 0
Meridian |  | Fuel Surcharge | 0 | 28.4067 | 0
Meridian |  | Dest Fee | 0 | 6.35 | 0
Meridian |  | Admin Fee | 0 | 2.5 | 0
Meridian |  | Environmental Fee | 0 | 11.9467 | 0
Meridian |  | Inv 1 | 0 | 73.13 | 0
Meridian |  | inv 2 | 0 | 472 | 0
Gigi'sBuld Removal | 2023-10-11 |  | 1 | 800 | 800
Refrigerator cleaning | April '24 |  | 1 | 150 | 150
Maid To Shine | cleaning |  | 1 | 420 | 420
AvilaCRI
[6 empty] | 0 | 0

## Appliances
Appliances
Description | ITEM | Quanity | Cost/Unit | Sub-Total | Tax | Total
HD Microwave | 1002724373 | 1 | 348 | 348 | 25.23
FB Marketplace Ref |  | 0 | 400 | 0 | 0
HD Dishwasher |  | 1 | 448 | 448 | 32.48
HD Range | 1006201314 | 1 | 748 | 748 | 54.23
1655.94
Dishwasher Hose |  | 1 | 31.98 | 31.98 | 2.3185 | 0
Ice Connector | L247027 | 1 | 14.98 | 14.98
Dishwasher Hose | 1630551 | 0 | 32.98 | 0 | 0
Lowes Range | 3648606 | 0 | 560.31 | 0 | 0
Lowes Dishwasher | 1654366 | 0 | 374.29 | 0 | 0
Lowes Range cord | 118694 | 0 | 39.28 | 0 | 0
Kitchen Sink |  | 0 | 189 | 0 | 0
HD Range Cord | 206332 | 1 | 32.85 | 32.85 | 2.3816
Kitchen faucet |  | 0 | 169 | 0 | 0
Lowes Microwave | 1692925 | 0 | 170.39 | 0 | 0
FB Ref |  | 0 | 400 | 0 | 0
|  | Total for Appliances: |  |  |  | 1740.4502

## Plumbing Fixtures
Plumbing
Description | ITEM | Quanity | Cost/Unit | Sub-Total | Tax | Total
|  | 0 | 107.1 | 0 | 0
Lowes Kitchen Faucet | 1255143 | 0 | 107.1 | 0 | 0
Lowes Bath Accessory Kit | 2131173 | 0 | 53.98 | 0 | 0
Lowes Shower Head | 1227792 | 0 | 15.47 | 0 | 0
Lowes Bath Faucets | 1233228 | 0 | 39.98 | 0 | 0
Amazon TP holders |  | 2 | 6.99 | 13.98 | 1.0135
Amazon accessory kit |  | 1 | 24.4 | 24.4 | 1.769
toilets |  | 0 | 99 | 0 | 0
Garbage Disposal | 26508261804 | 1 | 114 | 114 | 8.265
Shower Head | 6925699939094 | 2 | 34.98 | 69.96 | 5.0721
Resurface tubs |  | 0 |  | 0 | 0
Kitchen Faucet | 38877656754 | 1 | 169 | 169 | 12.2525
toilets | 732291231619 | 3 | 99 | 297 | 21.5325
Instant Savings on Toilets |  | 1 | -29.7 | -29.7 | -2.1532
Washing Machine Pan | HD | 1 | 34.48 | 34.48 | 2.4998
Washing Machine Pan | Lowes | 1 | 38.29 | 38.29 | 2.776
Plumber repair baths x2 | GWE Plumbing | 1 | 431.66 | 431.66 | 31.2953
Faucet | HD 195205064039 | 1 | 29.98 | 29.98 | 2.1736
1279.5461

## Windows & Doors
Doors & Windows
Description | ITEM | Quanity | Cost/Unit | Sub-Total | Total
36" Exterior (R) Out Swing | 935605 | 0 | 209 | 0
36" Exterior (L) Out Swing | 935604 | 0 | 209 | 0
36" Exterior (L) In Swing | 935599 | 0 | 198.56 | 0
32" Exterior (R) Out Swing | 14005 | 0 | 179 | 0
32" Exterior (L) Out Swing | 14006 | 0 | 179 | 0
32" Exterior (L) In Swing | 935587 | 0 | 198.55 | 0
30" Interior (R) | 49504 | 0 | 103 | 0
30" Interior (L) | 49706 | 0 | 103 | 0
28" Interior (R) | 47025 | 0 | 99 | 0
28" Interior (L) | 47422 | 0 | 99 | 0
24" Interior (R) | 43359 | 0 | 95 | 0
Garage Door Repair 5/20/25 | Door Jam | 1 | 536.25 | 536.25
65 x 72" vinyl mini blinds | HD793478353234 | 5 | 75.48 | 377.4 |  | tax 21.89
Hinge Pin Door Stop | L553102 | 1 | 3.29 | 3.29 |  | tax
31 x 64"vinyl mini blinds | L889891 | 4 | 15.48 | 61.92 |  | tax
23 x 64" vinyl mini blinds | L889862 | 1 | 7.48 | 7.48 |  | tax
35 x 64" vinyl mini blinds | L889910 | 1 | 20.98 | 20.98 |  | tax
25x72" Mag mini blinds | L924753 | 1 | 41.98 | 41.98
Labor Tim Fleming hang blinds |  | 1 | 85 | 85
Bed/bath knob | HD50150H | 4 | 2.47 | 9.88
Lowes Front door kw powerbolt | 100619 | 0 | 79.98 | 0
Lowes Front door kw door handle | 287027 | 0 | 50.48 | 0
HD Ext Deadbolt combo |  | 0 | 69.47 | 0
Garage Door Repair | Top Notch | 1 | 396.83 | 396.83
Garage Door Opener | HDB2211T | 1 | 213.43 | 213.43
Door Stop 5 pack |  |  |  | 0
Door Stop 5 pack | 30699285174 | 1 | 12.93 | 12.93
Untry Door Handle | 883351469845 | 1 | 47.97 | 47.97
Keypad Deadbolt | 883351891448 | 1 | 69.97 | 69.97
Exterior Door Handle and lock kit | 883351396332 | 1 | 139 | 139
|  |  |  | 0 | 2024.31
0
2024.31

## Cabinets
Cabinets
Description | ITEM | Quanity | Cost/Unit | Sub-Total | Tax | Total
| B21R | 0 | 154 | 0 | 0
24" Arcadia Cab Master | 795984 | 0 | 144 | 0 | 0
SCR36 | SCR36 | 0 | 224 | 0 | 0
36 sink base | B24R | 0 | 152 | 0 | 0
Panel | PePR335 | 0 | 50 | 0 | 0
Sink Base | SB36B | 0 | 166 | 0 | 0
Base Cab | B12R | 0 | 104 | 0 | 0
Wall Cab | W1230R | 0 | 81.98 | 0 | 0
Wall Cab | W2730B | 0 | 143 | 0 | 0
Wall Cab | W2430B | 0 | 98.98 | 0 | 0
Diag Corner | DC2430R | 0 | 165 | 0 | 0
Lowes Vanity Master | 795984 | 0 | 144 | 0 | 0
| W2130R | 0 | 107 | 0 | 0
Wall Cab | W3014B | 0 | 112 | 0 | 0
Toe Kicks | Toe Kicks | 0 | 40.96 | 0 | 0
| Filler F331 | 0 | 18.28 | 0 | 0
|  | 0 | 0 | 0 | 0
Installation |  | 0 | 0 | 0 | 0
Buy from Lowes |  | 0 | 935.09 | 0 | 0
0
Cabinet Tops
Description | ITEM | Quanity | Cost/Unit | Sub-Total |  | Total
| surface 1 | 0 | 0 | 0 | 0
| surface 2 | 0 | 0 | 0 | 0
| surface 3 | 0 | 0 | 0 | 0
Estimate for Avila Vendor |  | 0 | 4345 | 0 | 0
|  | 0 | 0 | 0 | 0
0
Cabinet Hardware
Description | ITEM | Quanity | Cost/Unit | Sub-Total |  | Total
Vanities - Sun HS Warehouse |  | 0 | 1100 | 0 | 0
Satin Nick cabinet knob | 400390 | 0 | 2.05 | 0 | 0
Arched 3" Drawer pull | 376787 | 0 | 4.98 | 0 | 0
|  | 0 | 0 | 0 | 0
Lowes 10 pk Matte Black Knob | 2280072 | 0 | 18.97 | 0 | 0
HD Satin Nickel Knobs | 1000707539 | 0 | 1.98 | 0 | 0
0
AvilaCRI
[7 empty] | 4165 | 4165

## Paint
Paint |  |  | Calc Qty
Description | Sq Ft | Item # |  | Qty | Cost/Unit | Sub-Total | Tax | Total
Interior Wall Paint | 1898 | [5 empty] | 0
SW |  | 6509-48698 | 0.0079177 | 0 | 68.54 | 0 | 0
SW 5 gal Int wall paint |  | 6504-06788 |  | 5 | 50.24 | 251.2 | 18.212
SW 5 gal PM 400 0 FL Extra |  | 6503-62817 |  | 0 | 85.89 | 0 | 0
SW 5 gal B31W2151 Procl LTX SG Extra |  | 6510-16875 |  | 5 | 65.64 | 328.2 | 23.7945
5 gal Lowes Kilz |  | 185342 | 0.0039588 | 0 | 29.4 | 0 | 0
SW 5 gal A27W5050 Promar ceiling white |  | 6508-68102 |  | 10 | 33.49 | 334.9 | 24.2803
HD Behr Int/ext black paint |  | 389832 |  | 0 | 39.98 | 0 | 0
HD White Int/ext white paint |  | 985007 | 0.0011876 | 0 | 52.23 | 0 | 0
HD 5 gal Wh Flat Int ceiling |  | 814917 | 0.0059382 | 0 | 21.8 | 0 | 0
Valspar |  | L1028086 |  | 0 | 40 | 0 | 0
SW 5 gal D17W151 Cashmere LL Extra |  | 6504-06788 |  | 15 | 50.24 | 753.6 | 54.636
Kitchen Cabinets | 0
SW 5galover White | [5 empty] | 0 | 0
1898
Exterior Wall Paint | 0
5 Gal -Valspar Signature Signature flat |  | Stone Eagle HGSW1456 |  | 0 | 93 | 0 | 0
Deck Stain | 500 |  |  |  |  | 0 | 0
L Valspar Semi trans deck stain |  | Lowes 1028086 |  | 0 | 47.98 | 0 | 0
L Valspar solid porch stain |  | Lowes 1028091 |  | 0 | 48.98 | 0 | 0
|  |  |  | 0 |  | 0 | 0
[6 empty] | 0 | 0
|  |  |  | Lowes Sub Total for Paint |  |  |  | 1788.8228
Painter | [5 empty] | 0 |  | 0
Painter is in contract | 1898 | Inside |  | no | 2.41 | 0
Painter | 1898 | Front Porch |  | No | 3.37 | 0
Painter | 1898 | Back Porch |  | No | 1 | 0 |  |  | AvilaCRI
[8 empty] | 5750 | 5750

## Flooring
Floor
Description | Sq Ft | Item # | Qty | Cost/Unit | Sub-Total | Total
1898
LVP Floor Installation | 949 | Inside | no | 3.2249 | 0 |  | in contract
LVP Floor Availa Vender | 949 |  | no | 2.69 | 0
LVP Floor RediCarpet #1 | 1898 |  | No | 1 | 0 |  |  |  | AvilaCRI
[8 empty] | LVP | 3790
LVP Floor |  |  |  |  | 0 |  |  | carpet | 2815
[6 empty] | 6605 |  | Total | 6605

## HVAC
HVAC
Description | Item | Quanity | Cost/Unit | Sub Total | Total
New unit | True Service HVAC | 0 | 7000 | 0
A/C registers | Lowes 66848 | 0 | 8.98 | 0
A/C registers | HD 4x10 803492136468 | 0 | 7.98 | 0
A/C Return Vent | Lowes 20x25 753897 | 0 | 44.93 | 0
AC Filter | HD 20x25 31949488390 | 0 | 4.47 | 0
AC Filter | Lowes 20x20 259930 | 0 | 4.97 | 0
True Srv Gas Call |  | 1 | 101.89 | 101.89
HVAC | True Service HVAC | 1 | 9402.61 | 9402.61
HVAC Service |  | 0 | 11504 | 0
9504.5

## Electrical Fixtures
Electrical
Description | ITEM | Quanity | Cost/Unit | Sub-Total | Total
0
Lowes Bedroom Ceiling Fans | 2599776 | 0 | 124.98 | 0
Lowes Liv Rm Ceiling Fan | 807421 | 0 | 112.48 | 0
Lowes 4light bath vanity | 321702 | 0 | 89.98 | 0
Lowes Flush Kitchen Light | 649829 | 0 | 129.98 | 0
Lowes Pendant Dining Light | 2296055 | 0 | 179.98 | 0
Lowes Ext Motion Lights | 482287 | 0 | 62.98 | 0
Lowes 2' Strip Light Mast Closet | 2535475 | 0 | 24.98 | 0
Floor registers | HD1002265221 | 0 | 10.9 | 0
Lowes 6" Canned fixture porch | L1100119 | 1 | 28.98 | 28.98
Outdoor flood light fixture | HD233840 | 0 | 19.97 | 0
Smoke & CO2 | HD1003181539 | 1 | 59.97 | 59.97
Flood Light Bulbs | HD1006248217 | 0 | 16.98 | 0
Breakers | HD047569062704 | 2 | 6.63 | 13.26
3 speed Remote ceiling fan | L745359 | 1 | 39.98 | 39.98
GE LED 32W 4' | L2565452 | 2 | 19.98 | 39.96
GE LED 17W 2' | L2565467 | 1 | 13.98 | 13.98
Smoke Detectors | HD2343598 | 4 | 19.97 | 79.88
Flush Kitchen Light | 46335120372 | 1 | 99.97 | 99.97
CeilingFan | 792145370178 | 1 | 59.97 | 59.97
Ceiling Fan | 82392573331 | 1 | 109 | 109
Lowes Tube light bulbs (2pack) | 5190530 | 3 | 18.98 | 56.94
Tube light return refund |  | 1 | -19.98 | -19.98
581.91

## Landscape
Landscape
Item | Cost/sf | Square Feet | Quanity | cost/unit | SubTotal | Total
Liesure Time Zoysia-pallet | 0.79 | 500 | 0 | 60 | 0
Liesure Time Zoysia-roll | 1 | 240 | 0 | 60 | 0
Delivery Fee |  |  | 0 | 150 | 0
Fence |  |  | 0 | 3000 | 0
organic humis |  |  | 0 | 165 | 0
Mowing 5/4/24 | Greenview wks |  | 1 | 60 | 60
Mulch Labor: |  |  | 0 | 15 | 0
Straighten landscape stones |  |  | 0 | 1100 | 0
Mowing Apr 6 | Greenview wks |  | 1 | 60 | 60
Tree pruning |  |  |  | 1000 | 0
Mowing, clean up yard | Greenview wks |  | 1 | 90 | 90
remove debris |  |  | 0 | 800 | 0
|  | 740 |  |  | Total | 210

## Exterior
Roof
Item | Qty | Cost/item | Total | Hourly Rate: | 20
Termite Treatment | 0 | 800 | 0
Lowes Mailbox | 0 | 28.46 | 0
Mailbox post HD106052 | 0 | 32.98 | 0
Mailbox HD 046462011291 | 1 | 28.47 | 28.47
Mailbox Numbers | 4 | 2.83 | 11.32
Siding Repair |  | 1000 | 0
Drainage repair |  |  | 0
Drainage repair |  |  | 0
Deck rebuild | 0 | 5500 | 0
Masking tape |  | 1604326 | 0
Drop cloths |  | 228556 | 0
Power wash | 0 | 400 | 0 |  |  |  | AvilaCRI
Weatherproof flat cover 852944007702 | 1 | 7.33 | 7.33
Doorbell 058219105177 | 1 | 9.97 | 9.97
| 1 | 9.97 | 9.97
Fence Picket 090489133771 | 1 | 3.98 | 3.98
New rear Fance Kaba Fence | 1 | 830 | 830 |  |  | 71.04